## Decision Log
# | Date | Summary | Issue | Decision | Next Action
1 | 2011-07-18 | Fork OntoWiki Code | Fork OntoWiki Code? PRO FORK: easier to deploy on new instances and release CON FORK: will have to merge with OntoWiki for future OntoWiki versions. | Fork code as we will most likely only need updates which are code fixes | Code Forked as of 7/18
2 | 2011-07-18 | Open ID / FOAF+SSL | Do we want to allow login with Open ID and FOAF? Currently the application allows registration via OpenID or FOAF. o PRO: (1) Some people may want to use an existing login rather than creating another login/password for this application. Easier access may increase use of application. (2) This functionality already exists in the application. The toggle to remove via “Configure Extensions” doesn’t seem to be working correctly. o CON: (1) Existing code treats registration via OpenID or FOAF as a default user, which would have no more rights than if someone were Anonymous. (2) Not clear how we would integrate these profiles into our existing user base (and how to require additional information such as “institution”). May be more work to integrate than to disable. | 7/26/11: OpenID seems reasonable. Investigate further how FOAF works - do we need a server-side certificate? 7/25/11 Let's table this removal to the end of development . Current estimate of work: 2 days. In the meantime, re-enable the OpenID/FOAF extension. 7/18/11:Remove Open ID/ FOAF+SSL. It's an extension so should be easy (in theory) to remove from extensions panel (OntoWiki (Admin): Extras> Configure Extensions…). (1) It is not a requirement. (2) It will be more work to integrate into our user system than to disable it. (3) We can always add it in for Version 2.0 | Lisa to check out what is required for FOAF.
3 | 2011-07-18 | Reviewer/Editor | Currently both the Editor and Reviewer inherit rights from the Contributor Role. However, it’s possible that, given small numbers of use, that one person may hold both roles of Editor and Reviewer. We were wondering if it makes sense that the Reviewer also inherit rights from Editor such that rights are hierarchical: . Editor inherits all rights from Contributor . Reviewer inherits all rights from Editor . Admin inherits all rights from Reviewer | Let Reviewer inherit all rights from Editor. | Implement roles with Reviewer inheriting from Editor
4 | 2011-07-18 | Review tag at instance level/triple level | The "Review" tags will exist on the "Triple" level - much like the Audit History.. As extra columns in that table. However, we need to decide whether the "Review" tag is applied *per instance* or *per triple*. PRO INSTANCE: From a usability POV, (and perhaps from a governance perspective), it may be easier to state "Approval" at the instance level as a button at the top of the page. It may be seen as not user-friendly to have to approve low-level triple statements. PRO TRIPLE: Someone may just want to approve a single statement and not have to read all the statements about the instance (or have the ability to judge all statements). For usability, one could offer a "check all boxes" option | Set approval at triple-level. Allow a "check all boxes" option. | Implement Review at triple level. In addition add an additional "Action Type" ("Statement reviewed") in the "History" tab.
5 | 2011-07-18 | contributor self-service or admin? | Is user-access to UDFR self-administrative or through an administrative console? If we decided to have an administrative/governance process for Contributor role contribution, what will it be? | Our proposal is to initially implement the Contributor role as self-service, but using Captcha to avoid spam. The Editor and Reviewer roles will be administered through an administrator. CDL will be the initial administrator. | Implementing our proposal. Question is out to the Stakeholder Community
6 | 2011-07-18 | terms of use - provenance | Our proposal for terms of use is to have the Real Name and Institution affiliation to be publically visible as provenance information. Is this acceptable? If not, what would be a suitable presentation so that UDFR users can make good judgments regarding provenance while maintaining privacy of editors? | Implement with Real Name and Institution for now. Question is out to the Stakeholder Community. | Implement with Real Name and Institution.
7 | 2011-07-18 | licensing materials in terms of use policy? | Should there be an explicit statement of licensing materials in our Terms of Use policy? | Question is out to the Stakeholder Community. Wondering if this would restrict those from providing information. Would be too difficult to have on triple by triple basis. So, would provide licencing - restricted to UDFR model. If there is embargo information, could put in other model. | Implement registration with an explicit Terms of Use Link.
8 | 2011-07-18 | what is license of materials? | What is the Licensing for the content of the UDFR? CC0? (Creative Commons) | Question is out to the Stakeholder Community. | Lisa to investigate other licensing options & follow-up with Tracey regarding any licensing of PRONOM. Leaning towared a CC-by, but need to check on compatibility with OGL for PRONOM
9 | 2011-07-18 | logo | Have preliminary logo - but needs to be implemented via web link to external site? If we use, perhaps we can redesign a bit. | Sent to Stakeholder Community for review. | Lisa to edit logo
10 | 2011-07-25 | user register user | Can a user register a new user? – assuming the process is the same to register a new user (fill in information plus a captcha), do we want to allow an existing user to register a new user? o PRO: (1) A manager can register team members (2) This functionality already exists in the application. o CON: (1)To register, one must give a password, so the end-user would need to change their password. (2) Since anyone can register themselves (with captcha), there really isn’t a *need* for someone to register anyone else. | 7/26/11 Disable this function. Require individuals to register themselves | Implement only Admin and Anonymous to be able to "register user"
11 | 2011-07-25 | dereferenceable URIs | Should UDFR classes exist as their own web pages on udfr.org? Currently there is functionality to “see resource (externally). What this does is link to a page given the UDFR base URI (http://www.udfr.org/udfr#) o PRO: (1) This is standard representation for dereferenceable URIs. (2) This functionality already exists in the application (which points to the base URI for the model) o CON: (1) We don’t currently own udfr.org. We will need to convince Andrea. (2) How will this work with using EZID? Will we still keep http://www.udfr.org/udfr# as base URI and have the UDFR ID be a separate property? I think that is how we planned it, just wanted to be sure it wouldn’t cause any problems. | Need to contact Andrea re:website. Question still out regarding EZID | Stephen to ask Andrea re:website. Perhaps all wiki can be consolidated on bitbucket. Possibly use udfr.net
12 | 2011-07-25 | Contributor create new knowledge bases? | Should contributor be able to create a new knowledge base? Current functionality links editing resources in a generic sense. If some has access to create a resource, they can create any resource, be it a class, instance or knowledge base itself. o PRO: (1) We may want to allow the flexibility for someone to create their own knowledge base as an extension of UDFR or perhaps a restriction of it. Or perhaps even a separate KB altogether (e.g. scientific data sets for DataONE) (2) the functionality already exists. o CON: (1) It is probably better to restrict this level access to administrators only so as not to confuse the user experience for the average user. (2) It’s not a requirement, further, people expect this to be the application that manages UDFR data, not other data. (3) If one were to import other data (e.g. PRONOM linked data), it would not necessarily be the authoritative copy. Without governance, this functionality would be less useful. | 7/26/11 Only let Admin create new knowledge base | Implement it so that only admin can add a new knowledgebase.
13 | 2011-08-05 | Can Reviewer rollback changes? | Originally we had decided that only the Administrator could rollback changes. However, it might be useful for a reviewer to rollback changes that they disagree with. . PRO: (1) In cases where there is some spam or large quantities of bad statements, the reviewer can rollback, not be dependent on the administrator as roadblock (since CDL may not have lots of resources available for admin maintenance). This allows the "community" to police themselves. . CON: Anyone already has the ability to remove statements. This is captured in the history. | no
14 | 2011-08-11 | Can a statement be "un-reviewed"? | We have decided to use a simplified approach to Reviewer actions and history in the interest of time. Should we have more development time after all the core functionality is developed, we can revisit. For now: 1. Do not allow re-review of a statement. Once a statement is reviewed, it cannot be done by another reviewer. In other words, there is no “un-review” action: -> show greyed out check-boxes under "review". once reviewed, these boxes are un-actionable. 2. Further, even the Admin can not change the “review” status. There will be no rollback: -> show "rollback changes" as greyed out. also don't allow selection of those actions who are "statement reviewed" 3. Currently the reviewer’s name will show up under the “User” tab (as above). This won’t be a clickable resource. | no, not even for administrator
15 | 369491 | Source Code Flow | We have four source code repositories that we are potentially changing for this project: OntoWiki, Zend, RDFauthor and Erfurt. Erfurt is maintained in a Git repository while the others are mercurial. | We have decided to set up a forked Git repository in order to ease future code merging. So, the three mercurial repositories will be synced to CDL HG server (and eventually copied to the UDFR bitbucket site) while the Erfurt git repository will be forked to our own git repository. The VM Dev machine will query/pull and reference code from the CDL HG server and the UDFR Erfurt git repository. | yes
| 2011-08-19 | Reviewing Format Relations | Which of the GDFR format relations do we want to support? How will they be defined? | Use LC-format relationships: (1) subtype, (2)version, (3) contain. Use GDFR: (as descriptive - not set-theoretical) (1) extension, (2) restriction, (3) modification. Delete (1) definition, (2) containment (semantic/serial), (3) equivalent (semantic/syntactic), (4) format family | yes
| 2011-08-23 | Removing Editor Role | Should we remove the editor role? | There isn't a requirement for this role above others. As the entire registry is intended to be controlled, no reason why this certain class of enumerations should be treated differently from other elements.
| 2011-08-29 | Cardinality representation | Should cardinality be expressed in OWL cardinality constraints or can we just create cardinality properties on properties as DCMI did? | just use cardinality as a property
| 2011-08-30 | Importing Existing ontologies | Do we import ontologies that exist in the wild? | PRO: for our interface, we want to be able to express these controlled vocabularies as pulldown lists which will be difficult if only individual URIs are available on the web. We also need to be concerned about the persistence of connectivity in downloading external resources. We will download the appropriate ontologies, and add additional bookeeping information (such as ontology version and date) to the ontologies that are imported.
| 2011-08-30 | One profile | Do we want to have one profile for individuals and organizations? PRO: one profile will be easier to implement. CON: there may be some properties that are limited to one type of agent (inividual or group) which is disjoint. However, this isn't really a problem because both individual and group name will be required for any profile, so the rest of the properties can just be attributed to the values for individuals and groups, respectively.
| 2011-08-23 | email in profile | Should e-mail be a text string or a "mailto" URI? Also, should we use HSA1 encryption? Can we decrypt it?
| 2011-09-01 | EZID? | What will get EZIDs? Or do we use NOID minters. Issue with using EZID service for ARK creation, is that, while we're hosting it, it's free, but there would be a cost if hosted elsewhere. | Create two NOID minters. One for Formats/Compression Algorithms/Character Encodings. By having two minters, we can keep the ID numbers down for formats. We will need to register our format shoulder with EZID. Suggestion is for Format shoulder to be "F0". The other shoulder can be longer, like, "UDFR" . Also we will want to set up a process where we pass the metadata we have to EZID. | We are thinking we need to have node identifiers in there as well, so as not to have identifier collision. See: https://confluence.ucop.edu/display/UC3/EZID+identifiers
| 2011-09-05 | embargo data | Cases: (1) Can be distributed and visible, (2) Not distributed and not visible and (3) (?) Can be distributed but not visible (is thisa use case?) Discussed whether Terms of Use should be at User level or at data level (at point of edit). Technically, difficult as all rights are at the model level. Recommend having Terms of Use be linked to repository. Generally, people give up rights for the Public Repository, but can retain some rights for the Private Repositories. | Will experiment with creating separate models which can be used as private repositories
| 2011-09-01 | modularize ontology | should ontology be broken down into modules? | no
| 2011-09-07 | editing UDFR schema | How does one make adjustments to the current UDFR model? Will we allow editing of the model within the registry? Or will someone need to change the model using a tool outside of the registry? | Editing of the UDFR model will be done *outside* of the registry and imported. Because we want URIs to be stable for imports, we should allow OntoWiki-defined URIs for the model, rather than NOID-service generated ones.
| 2011-09-20 | boolean format? | boolean represented as 1/0, true/false, yes/no,…? | represent as true/false
| 2011-09-20 | representing aliases

## Defer - UDFR v2
Date | Feature | Issue

## magic registered
FID | Comment | Ext. | Software | Submitter | Magic type
000001008-00-0000001 | Wordperfect help file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect application resource library |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect block file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect column block |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect dictionary file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect dictionary rules file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect external spell code module file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect external spell dictionary file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect Graphics screen driver file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect hyphenation code module file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect hyphenation data module file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect hyphenation lex module |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect installation information file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect keyboard definition file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect macro data file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect macro resource file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect printer Q codes (used by VAX/DG) |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect rectangular block file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect spell code module rules file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect spell code module word list |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect thesarus file |  | Wordperfect | Carl
000001008-00-0000001 | Wordperfect VAX keyboard definition file |  | Wordperfect | Carl
000001008-00-0000ALL | Wordperfect printer resource file | all | Wordperfect | Carl
000001001-00-0000CON | Microsoft Animated cursor, little-endian | con |  | Carl
000001001-00-0000CON | Microsoft Animated cursor, big-endian | con |  | Carl
000001008-00-0000DOC | Macintosh Wordperfect document file | doc | Wordperfect | Carl
000001008-00-0000DOC | VAX Wordperfect document file | doc | Wordperfect | Carl
000001008-00-0000DRS | Wordperfect display resource file | drs | Wordperfect | Carl
000001008-00-0000FIL | Wordperfect overlay file | fil | Wordperfect | Carl
000001001-00-0000GRP | Microsoft windows group file | grp |  | Carl
000001007-00-000INFO | Amiga shortcut / icon file | info |  | Carl
000001008-00-0000INS | Wordperfect installation information file | ins | Wordperfect | Carl
000001001-00-0000LNK | Microsoft Windows shortcut file | lnk |  | Carl
000001008-00-0000PRS | Wordperfect printer resource file | prs | Wordperfect | Carl
000001008-00-0000QRS | Wordperfect 5.1 equation resource file | qrs | Wordperfect | Carl
000001008-00-0000SET | Wordperfect setup data | set | Wordperfect | Carl
000001001-0E-0000PAL | Microsoft Palette, little-endian | pal,riff |  | Carl
000001001-0E-0000PAL | Microsoft Palette, big-endian | pal,rifx |  | Carl
000000001-0F-0014863 |  |  |  | Carl
000001007-0F-0000ADF | AmigaOS File system | adf |  | Carl
000000001-0F-0009660 | CD-ROM file system | iso |  | Carl | MP
000001007-10-LIBRARY | Amiga Classic executable file (680x0 family) | ,library |  | Carl
000000003-10-000000O | COFF executable and linkable object file | ,o,out |  | Carl | NEM
000000003-10-000000O | Executable linkable file (ELF) | ,o,so,out |  | Carl
000000003-10-000000O | Executable linkable file (ELF) | ,o,so,out |  | Carl
000001001-10-0000EXE | New executable file | exe,dll |  | Carl
000001001-10-0000EXE | New executable file | exe,dll |  | Carl
000001001-10-0000EXE | Microsoft Windows 3.x New Executable file | exe,dll |  | Carl
000001001-10-0000EXE | Microsoft Windows 3.x New Executable file | exe,dll |  | Carl
000001009-10-0000EXE | IBM OS/2 New Executable file | exe,dll |  | Carl
000001009-10-0000EXE | IBM OS/2 New Executable file | exe,dll |  | Carl
000001001-10-0000EXE | Microsoft Windows NT Portable Executable file | exe,dll | Microsoft Windows | Carl
000001001-10-0000EXE | Microsoft Windows NT Portable Executable file | exe,dll | Microsoft Windows | Carl
000001001-10-0000EXE | Microsoft Windows Linear executable | exe,dll,drv | Microsoft Windows,DOS4GW | Carl
000001001-10-0000EXE | Microsoft Windows Linear executable | exe,dll,drv | Microsoft Windows,DOS4GW | Carl
000001009-10-0000EXE | OS/2 Linear executable | exe,dll,drv | OS/2,DOS4GW | Carl
000001009-10-0000EXE | OS/2 Linear executable | exe,dll,drv | OS/2,DOS4GW | Carl
000001025-10-0000HEX | Intel hexadecimal encoded object file | hex |  | Carl | MP
000001026-10-0000HEX | Tektronix hexadecimal encoded object file | hex |  | Carl | MP
000001024-10-0000S19 | Motorola srecord encoded object file | s19,hex |  | Carl | MP
000001001-10-0000TLB | Microsoft component type library | tlb |  | Carl
000001006-10-0000TTP | Atari MiNT executable/object file | ttp,gem,prg |  | Carl
000001006-10-0000TTP | Atari TOS executable/object file | ttp,gem,prg |  | Carl
000000000-10-0000VPI | Virtual pascal unit file | vpi | Virtual Pascal | Carl
000000006-11-0000695 | IEEE 695: Object file format |  | Microtec Research linker | Carl | MP
000001011-11-00CLASS | Javal virtual machine class file | class | Java compiler | Carl
000001005-11-0000DCP | Borland Delphi compiled package code file | dcp | Borland Delphi | Carl
000001005-11-0000DCU | Borland Delphi code unit file | dcu | Borland Delphi | Carl
000001005-11-0000TPU | Turbo Pascal 6.0 code unit file | tpu | Turbo Pascal | Carl
000001005-11-0000TPU | Borland Pascal 7.0 code unit file | tpu,tpp,tpw | Turbo Pascal, Borland Pascal | Carl
000001016-20-0000BNK | Adlib FM instrument bank file | bnk |  | Carl
000001013-20-0000IBK | Creative Labs FM instrument bank file | ibk |  | Carl
000001001-20-0000IDF | Microsoft instrument definition file, little-endian | idf | Microsoft Instrument Definition file | Carl
000001001-20-0000IDF | Microsoft instrument definition file, big-endian | idf | Microsoft Instrument Definition file | Carl
000100088-20-0000IST | Digitrakker Instrument file | ist | Digitrakker | Carl
000100032-20-0000ITI | Impulse tracker instrument file | iti | Impulse tracker | Carl
000100091-20-0000MTI | Madtracker instrument file | mti | Madtracker | Carl
000001018-20-0000PAT | Gravis Ultrasound Patch (old instrument data) | pat | Gravis Ultrasound | Carl
000001018-20-0000PAT | Gravis Ultrasound Patch (instrument data) | pat | Gravis Ultrasound | Carl
000001013-20-0000SBI | Creative Labs FM instrument data file | sbi |  | Carl
000000000-20-0000SID | SIDPlayer music file | sid | Sidplay | Carl
000100026-20-00000XI | FastTracker II instrument file | xi | Fasttracker 2.0 | Carl
000001001-21-0000000 | MIDI music file, little-endian |  |  | Carl
000001001-21-0000000 | MIDI music file, big-endian |  |  | Carl
000000000-21-0000669 | Composer 669 module music file | 669 | Composer 669 | Carl | NEM
000000000-21-0000669 | Composer 669 extended module music file | 669 | Composer 669 | Carl | NEM
000100029-21-0000AHX | AHX module music file | ahx | Abyss's highest experience (AHX) | Carl
000100034-21-0000AMD | Amusic Adlib tracker music file | amd | Amusic | Carl
000001276-21-0000AMS | Velvet Studio module music file | ams | Velvet Studio | Carl
000001301-21-0000AVR | Audio visual research audio file | avr | Audio visual research | Carl
000100028-21-00000BP | Soundmon module music file, version 2.x | bp | Soundmon | Carl
000100028-21-0000BP3 | Soundmon module music file, version 3.x | bp3 | Soundmon | Carl
000001013-21-0000CMF | Creative Labs music file | cmf |  | Carl
000100027-21-0000D00 | Edlib Adlib Tracker music file | d00 | Edlib Tracker | Carl | NM
000001302-21-000DIGI | Digibooster music file | digi | Digibooster | Carl
000000000-21-0000DMF | Delusion tracker module music file | dmf | Delusion Xtracker | Carl
000000000-21-0000DSM | DOS Sound interface kit module music file | dsm | DOS Sound interface kit (DSIK) | Carl
000100027-21-0000EDL | Edlib FM tracker music file | edl | Edlib | Carl
000100085-21-0000EMD | Enhanced module music file (IFF) | emd | Quadra Composer | Carl
000100087-21-0000FAR | Farandole composer module music file | far | Farandole composer | Carl
000100086-21-0000FNK | Funktracker Gold music file | fnk | Funktracker Gold | Carl
000001280-21-0000GDM | General DigiMusic module music file | gdm | Bells, Whistles, and Sound Boards | Carl
000100031-21-0000GT2 | Graoumf Tracker module music file | gt2 | Graoumf Tracker 2 | Carl
000001279-21-0000IMF | Imago morpheus music file, 32 channels | imf | Imago Morpheus | Carl
000001303-21-0000IMS |  | ims | Images Music System | Carl
000100032-21-00000IT | Impulse Tracker module music file | it | Impulse tracker | Carl
000000000-21-0000JAM | Jamcracker tracker module music file | jam | Jamcracker | Carl
000100090-21-0000LIQ | Liquid tracker module music file | liq | Liquid tracker | Carl
000100088-21-0000MDL | Digitrakker module music file | mdl | Digitrakker | Carl
000001278-21-0000MED | Octamed tracker module music file | med | MED Soundstudio / OctaMED | Carl
000001278-21-0000MED | Octamed Pro Tracker module music file | med | MED Soundstudio / OctaMED | Carl
000001278-21-0000MED | Octamed Pro Tracker module music file | med | MED Soundstudio / OctaMED | Carl
000001278-21-0000MED | Octamed Sound Studio module music file | med | MED Soundstudio / OctaMED | Carl
000001304-21-00000ML | Musicline module music file | ml | Musicline | Carl
000100022-21-0000MOD | Protracker 2.3 module music file | mod | Protracker | Carl
000100022-21-0000MOD | Protracker module music file | mod | Protracker | Carl
000100022-21-0000MOD | Protracker module music file, version 3.x | mod | Protracker | Carl
000100024-21-0000MOD | Startrekker module music file, 4 channels | mod | Startrekker | Carl
000100024-21-0000MOD | Startrekker module music file, 8 channels | mod | Startrekker | Carl
000001275-21-0000MOD | Fasttracker module music file, 6 channels | mod | Fasttracker | Carl
000001275-21-0000MOD | Fasttracker module music file, 6 channels | mod | Fasttracker | Carl
000100091-21-0000MT2 | Madtracker module music file | mt2 | Madtracker | Carl
000100089-21-0000MTM | MultiTracker module music file | mtm | Multitracker Module editor | Carl
000100091-21-0000MTP | Madtracker pattern file | mtp | Madtracker | Carl
000100094-21-0000NSA | A/NES ripped audio file | nsa | A/NES | Carl
000100093-21-0000NSF | NES ripped audio file | nsf |  | Carl
000100023-21-0000NST | Noisetracker module music file | nst | Noisetracker | Carl
000100030-21-0000OKT | Oktalyzer module music file | okt | Oktalyzer tracker | Carl
000100020-21-0000PAC | SBStudio module music file | pac | SBStudio sound | Carl
000000000-21-0000PTM | Poly Tracker module music file | ptm | Polytracker | Carl
000000000-21-0000RAD | Reality Adlib tracker music file | rad | Reality Adlib tracker | Carl
000000000-21-0000RMI | Song notation data file, little-endian | rmi |  | Carl
000000000-21-0000RMI | Song notation data file, big-endian | rmi |  | Carl
000001016-21-0000ROL | Adlib music file | rol | Adlib Visual Composer | Carl
000100025-21-0000S3M | Scream tracker module music file | s3m | Screamtracker 3 | Carl
000100021-21-0000SA2 | Surprise Productions Adlib tracker music file | sa2 | Surprise! Adlib Tracker | Carl
000001277-21-0000SFX | SoundFX Tracker module music file | sfx | SoundFX | Carl
000000000-21-0000SID | PlaySID music file | sid | PlaySID, Sidplay | Carl
000001017-21-0000SMF | Standard MIDI music file | smf,midi |  | Carl
000001010-21-000SMUS | IFF Simple Musical Score file | smus,mus |  | Carl
000000000-21-0000SND | Nintendo Entertainment System audio file (NES) | snd | Sndtool2,nezplay | Carl
000100092-21-0000SND | iNES emulator audio file | snd | iNES | Carl
000100025-21-0000STX | STMIK module music file | stx | STMIK | Carl
000100096-21-0000TFX | TFMX tracker module music file | tfx,tfmx | The Final Musicsystem eXtended (TFMX) | Carl
000100097-21-0000ULT | Ultra Tracker module music file | ult | Ultra Tracker | Carl
000000000-21-0000UNI | APlayer module music file | uni | APlayer | Carl
000000000-21-0000UNI | Mikmod module music file | uni | Mikmod | Carl
000100026-21-00000XM | FastTracker II module music file | xm | Fasttracker 2.0 | Carl
000001010-22-0008SVX | Amiga Sampled audio file | 8svx |  | Carl
000001002-22-000AIFC | Audio Compressed Interchange File Format | aifc,aif |  | Carl
000001002-22-000AIFF | Audio Interchange File Format | aiff,aif |  | Carl
000100120-22-0000APE | MonkeyAudio compressed audio file | ape | MonkeyAudio software | Carl
000001011-22-00000AU | Sun / NeXt sampled audio file | au,snd |  | Carl
000001019-22-000000D | Sppack audio sample file | d | Sppack | Carl
000100098-22-000FLAC | Free Lossless Audio Codec raw audio file | flac | Flac | Carl
000100087-22-0000FSM | Farandole composer audio sample file | fsm | Farandole Composer | Carl
000000000-22-000MAUD | MAUD audio sample file | maud | MAUD | Carl
000000001-22-0011172 | MP3 Audio stream file | mp1,mp2,mp3 |  | Carl
000000001-22-0011172 | MP3 Audio stream file | mp1,mp2,mp3 |  | Carl
000001014-22-00000SF | IRCAM audio sample file | sf |  | Carl
000001014-22-00000SF | IRCAM audio sample file, little-endian | sf |  | Carl
000001014-22-00000SF | IRCAM audio sample file, big-endian | sf |  | Carl
000001014-22-00000SF | IRCAM audio sample file | sf |  | Carl
000001014-22-00000SF | IRCAM audio sample file, big-endian | sf |  | Carl
000001014-22-00000SF | IRCAM audio sample file, little-endian | sf |  | Carl
000001014-22-00000SF | IRCAM audio sample file, big-endian | sf |  | Carl
000100025-22-0000SMP | Screamtracker audio sample | smp | Screamtracker | Carl
000100095-22-0000SND | Sound tool audio data file | snd | SoundTool | Carl
000100020-22-0000SOU | SBStudio sampled audio file | sou | SBStudio | Carl
000000000-22-00SPEEX | Speex Lossy Audio Codec raw audio file | speex |  | Carl
000001013-22-0000VOC | Creative Voice audio file | voc | Sound Blaster SDK | Carl
000000000-22-0VORBIS | Vorbis Lossy Audio Codec raw audio file | vorbis |  | Carl
000001001-22-0000WAV | Microsoft Waveform Audio file, little-endian | wav |  | Carl
000001001-22-0000WAV | Microsoft Waveform Audio file, big-endian | wav |  | Carl
000001312-31-0000000 | Maya image file |  | Maya | Carl
000001312-31-0000000 | Maya image file |  | Maya | Carl
000001023-31-0000ART | AOL/Johnson-Grace image file, version 2.0 | art | AOL | Carl
000100048-31-0000BMF | BMF image file | bmf | BMF image compressor | Carl
000100048-31-0000BMF | BMF image file | bmf | BMF image compressor | Carl
000100048-31-0000BMF | BMF image file | bmf | BMF image compressor | Carl
000001001-31-0000BMP | Windows or OS/2 Bitmap image file | bmp |  | Carl
000001254-31-0000CEL | Autodesk animator image file | cel,pic | Autodesk Animator | Carl
000001315-31-0000CMU | Andrew toolkit raster image file | cmu | Andrew User Interface System | Carl
000100104-31-0000COD | Anivga sprite image file | cod | Anivga toolkit | Carl
000001001-31-0000CUR | Microsoft windows cursor image file | cur | Windows Cursor | Carl
000001001-31-0000CUR | Microsoft windows cursor image file | cur | Windows Cursor | Carl
000001001-31-0000CUR | Microsoft windows cursor image file | cur | Windows Cursor | Carl
000001001-31-0000CUR | Microsoft windows cursor image file | cur | Windows Cursor | Carl
000001001-31-0000CUR | Microsoft windows cursor image file | cur | Windows Cursor | Carl
000001001-31-0000CUR | Microsoft windows cursor image file | cur | Windows Cursor | Carl
000001257-31-0000DCX |  | dcx | PC-Paintbrush | Carl
000000004-31-000DICM | Digital imaging and communication in medecine img. | dicm,dcm |  | Carl
000001309-31-0000DPX | Digital Moving-Picture Exchange image file | dpx |  | Carl
000001309-31-0000DPX | Digital Moving-Picture Exchange image file | dpx |  | Carl
000001251-31-000FPBM | Flexible Precision Buffer Map image file | fpbm | Lightwave 3D | Carl
000001274-31-0000GIF | GIF image file | gif |  | Carl
000001274-31-0000GIF | GIF image file | gif |  | Carl
000001001-31-0000ICO | Microsoft windows Icon image file | ico | Windows Icon | Carl
000001001-31-0000ICO | Microsoft windows Icon image file | ico | Windows Icon | Carl
000001001-31-0000ICO | Microsoft windows Icon image file | ico | Windows Icon | Carl
000001001-31-0000ICO | Microsoft windows Icon image file | ico | Windows Icon | Carl
000001001-31-0000ICO | Microsoft windows Icon image file | ico | Windows Icon | Carl
000001001-31-0000ICO | Microsoft windows Icon image file | ico | Windows Icon | Carl
000001011-31-000ICON | SunOS icon image file | icon | SunOS Icon | Carl
000100114-31-0000IMG |  | img | Vivid ray tracer | Carl | NM
000001273-31-0000IMG | GEM Bit Image | img |  | Carl
000000000-31-0000JNG | JPEG Network graphics image file | jng |  | Carl
000000001-31-0015444 | JPEG 2000 image file | jp2 |  | Carl
000000001-31-0015444 | JPEG 2000 code stream image file | jpc |  | Carl
000001305-31-000JPEG | Joint Photographic Experts Group JFIF image file | jpeg,jpg |  | Carl
000000005-31-000JPEG | Digital still camera image file | jpg,jpeg |  | Carl
000001010-31-0000LBM | Interleaved bitmap image file | lbm | Deluxe Paint | Carl
000000000-31-000LISP | Lisp machine format image file | lisp |  | Carl
000001316-31-0000MDA | Microdesign Area image file | mda | Microdesign2, Microdesign3 | Carl
000001316-31-0000MDP | Microdesign page image file | mdp | Microdesign2, Microdesign3 | Carl
000000000-31-0000MGR |  | mgr | MGR Window system | Carl | NEM
000100101-31-000MIFF | Imagemagick image file | miff,mif | Imagemagick | Carl
000100105-31-0000MRF | Monochrome recursive format image file | mrf | Netpbm | Carl
000001001-31-0000MSP | Microsoft paint image file, version 1.0 | msp | Microsoft Paint | Carl
000001001-31-0000MSP | Microsoft paint image file, version 2.0 | msp | Microsoft Paint | Carl
000100100-31-0000PAM | Portable arbitrary map image file | pam | Netpbm | Carl
000100100-31-0000PBM | Portable bitmap image file, ascii | pbm | Netpbm | Carl
000100100-31-0000PBM | Portable bitmap image file, binary | pbm | Netpbm | Carl
000001257-31-0000PCX | PC-Paintbrush image file, version 2.5 | pcx | PC-Paintbrush | Carl
000001257-31-0000PCX | PC-Paintbrush image file, version 2.8 | pcx | PC-Paintbrush | Carl
000001257-31-0000PCX | PC-Paintbrush image file, version 2.8 | pcx | PC-Paintbrush | Carl
000001257-31-0000PCX | PC-Paintbrush for windows image file | pcx | PC-Paintbrush | Carl
000001257-31-0000PCX | PC-Paintbrush image file, version 3.0 | pcx | PC-Paintbrush | Carl
000001257-31-0000PCX |  | pcx | PC-Paintbrush | Carl
000100100-31-0000PGM | Portable gray map image file, ascii | pgm | Netpbm | Carl
000100100-31-0000PGM | Portable gray map image file, binary | pgm | Netpbm | Carl
000001318-31-0000PIC | Pictor PC Paint image file | pic | PC Paint | Carl
000001318-31-0000PIC | Pictor PC Paint image file | pic | PC Paint | Carl
000001318-31-0000PIC | Pictor PC Paint image file | pic | PC Paint | Carl
000001321-31-0000PIC | Softimage 3D image file | pic | Softimage 3D | Carl
000001322-31-0000PIC | Bio-rad confocal microscope image file | pic | Bio-rad microscope | Carl
000001311-31-0000PIX |  | pix | Hijaak pro, Workdstar, Multimate | Carl | NM
000000001-31-0015948 | Portable Network Graphic file | png |  | Carl
000100100-31-0000PPM | Portable pixel map image file, ascii | ppm | Netpbm | Carl
000100100-31-0000PPM | Portable pixel map image file, binary | ppm | Netpbm | Carl
000001003-31-0000PSD | Adobe Photoshop image file | psd | Photoshop | Carl
000001310-31-0000PSP | Paintshop pro image file | psp | Paint shop pro | Carl
000001011-31-0000RAS | Sun raster image | ras |  | Carl
000001004-31-0000RGB | SGI Image file | rgb |  | Carl
000001004-31-0000RGB | SGI Image file | rgb |  | Carl
000001004-31-0000RGB | SGI Image file | rgb |  | Carl
000001004-31-0000RGB | SGI Image file | rgb |  | Carl
000001004-31-0000RGB | SGI Image file, compressed | rgb |  | Carl
000001004-31-0000RGB | SGI Image file, compressed | rgb |  | Carl
000001004-31-0000RGB | SGI Image file, compressed | rgb |  | Carl
000001252-31-000RGB8 | Turbo Silver 24-bit RGB image file | rgb8,rgb | Turbo Silver | Carl
000001252-31-000RGBN | Turbo Silver 12-bit RGB image file | rgbn,rgb | Turbo Silver | Carl
000001312-31-0000RLA |  | rla | Wavefront Advanced visualiser | Carl | NM
000001314-31-0000SCT |  | sct |  | Carl | MP
000001320-31-0000SCZ | ColorRIX VGA Paint image file | scz | ColoRIX VGA Paint | Carl
000000000-31-0000SIR | Solitaire image recorder image file, MGI type 11 | sir |  | Bryan Henderson
000000000-31-0000SIR | Solitaire image recorder image file, MGI type 17 | sir |  | Bryan Henderson
000001306-31-0000TGA | Truevision Targa image file | tga |  | Carl
000001258-31-0000THN | Graphics workshop thumbnail image file | thn | Graphics Workshop | Carl
000001258-31-0000THN |  | thn | Graphics Workshop | Carl
000001003-31-0000TIF | Tagged image file format image file, little-endian | tif,tiff,dng |  | Carl
000001003-31-0000TIF | Tagged image file format image file, big-endian | tif,tiff,dng |  | Carl
000001313-31-0000URT | Utah raster toolkit run length encoded file | urt,rle | Utah Raster toolkit | Carl | NEM
000001022-31-0000VIC | Vicar image file | vic,vicar | VICAR | Carl
000001308-31-0000VIF | Khoros Visualization/Image File Format, version 1.3 | vif,viff | Khoros | Carl
000100107-31-0000WFA | Fractal Image And Sequence Codec image file | wfa |  | Carl
000001020-31-0000XPM | X-Windows pixel map image file | xpm | X-Windows | Carl
000100103-31-00000XV | XV Thumbnail image file | xv | XV | Carl
000001020-31-0000XWD | X10 XWindows dump image file | xwd | XWindows | Carl
000001020-31-0000XWD | X10 XWindows dump image file | xwd | XWindows | Carl
000001317-31-000ZINC |  | zinc | Zinc Interface library | Carl | NM
000001319-32-000DR2D | Provector 2D image file | dr2d | Provector | Carl
000100011-32-0000FIG | Facility for Interactive Generation file | fig | XFig, WinFig, jFig | Carl
000001009-32-0000PIC | Lotus 1-2-3 image file | pic | Lotus 1-2-3 | Carl
000001254-32-0000SLD | Autocad slide image file | sld | Autocad | Carl
000001008-32-0000WPG | Wordperfect Graphics vectors | wpg | Wordperfect | Carl
000100019-33-000AMFF | Amiga metafile | amff |  | Carl
000001003-33-0000APM | Aldus placeable Windows metafile | apm |  | Carl
000001008-33-0000CDR | Coreldraw little-endian metafile | cdr | CorelDRAW | Carl
000001008-33-0000CDR | Coreldraw big-endian metafile | cdr | CorelDRAW | Carl
000000001-33-0008632 | Computer graphics metafile, binary encoded | cgm |  | Carl
000000001-33-0008632 | Computer graphics metafile, ascii encoded | cgm |  | Carl
000001008-33-0000CMX | Corel little-endian metafile | cmx | CorelDRAW | Carl
000001008-33-0000CMX | Corel big-endian metafile | cmx | CorelDRAW | Carl
000001001-33-0000EMF | Microsoft Windows Enhanced metafile | emf |  | Carl
000001003-33-000EPSF | Adobe Encapsulated Postscript Level 2, version 1.2 | epsf |  | Carl
000001003-33-000EPSF | Adobe Encapsulated Postscript Level 2, version 2.0 | epsf |  | Carl
000001003-33-000EPSF | Adobe Encapsulated Postscript Level 3, version 3.0 | epsf |  | Carl
000001003-33-000EPSF | Adobe Encapsulated Postscript, version 3.0, binary | epsf,ai |  | Carl
000001273-33-0000GEM | GemDOS Motorola Metafile, version 1.01 | gem | GEM Paint | Carl
000001273-33-0000GEM | GemDOS Metafile | gem |  | http://www.seasip.info/Gem/ff_gem.html
000001273-33-0000GEM | GemDOS Intel Metafile, version 4.00 | gem | Artline | http://www.seasip.info/Gem/ff_gem.html
000001273-33-0000GEM | GemDOS Intel Metafile, version 3.10 | gem | Deskpress | http://www.seasip.info/Gem/ff_gem.html
000001273-33-0000GEM | GemDOS Intel Metafile, version 1.01 | gem | GEM Paint | http://www.seasip.info/Gem/ff_gem.html
000001002-33-0000PCT | Macintosh Quickdraw metafile 'PICT', version 2.0 | pct | Quickdraw | Carl
000001011-33-000PLOT |  | plot | UNIX | Carl | NM
000001001-33-0000WMF | Microsoft Windows metafile | wmf |  | Carl
000001255-40-0000000 | Maxon Cinema 4D version 5 3D data |  | Cinema 4D Version 5.x | Carl
000001324-40-00003D2 |  | 3d2 | Stereo CAD-3d | Carl | NEM
000001002-40-0003DMF | Apple Quickdraw 3D metafile | 3dmf | Quickdraw 3D | Carl
000001330-40-0003DMF | Rhino3d / OpenNurbs 3d model | 3dmf | Rhino 3d | Carl
000001002-40-0003DMF | Apple Quickdraw 3D metafile | 3dmf,a3d | Quickdraw 3D | Carl
000001326-40-00003DS | Autodesk 3d studio 3D model, binary encoded | 3ds | Autodesk 3D Studio | Carl | MP
000000000-40-00000AC | Ac3d 3d model | ac | AC3d | Carl
000100111-40-0000ART |  | art | Another ray tracer (ART) | Carl | NM
000001326-40-0000ASC | Autodesk 3d studio 3D model, ascii encoded | asc | Autodesk 3D Studio | Carl | NM
000001326-40-0000ASE | 3d studio max ascii export 3D model | ase | 3dStudio Max | Carl
000000000-40-0000BMF | OpeBasic model format 3d model | bmf | Openuniverse | Carl | NM
000100115-40-0000BRP |  | brp | Behemot editor | Carl | NM
000001331-40-0000BYU | BYU 3d model | byu | Ensight | Carl | NM
000001256-40-0000COB | Caligari Truespace2 3D model | cob,scn | Caligari Truespace Modeler | Carl
000100116-40-0000DAT | Tachyon ray-tracer 3d model | dat | Tachyon parallel raytracer | Carl
000001254-40-0000DWG | Autocad drawing format 3d model | dwg | Autocad | Carl
000001254-40-0000DXF | Autocad drawing interchange 3d model, binary | dxf | Autocad | Carl
000001254-40-0000DXF | Autocad drawing interchange 3d model, ascii | dxf | Autocad | Carl | NM
000001332-40-0000FLT | Openflight scene description 3d model | flt | Multigen creator | Carl
000001328-40-0000GEO | Videoscape 3d model with colored vertices | geo | Videoscape 3D | Carl
000001328-40-0000GEO | Videoscape 3d model with colored faces | geo | Videoscape 3D, Blender | Carl
000001328-40-0000GEO | Videoscape 3d model light source | geo | Videoscape 3D, Blender | Carl
000001328-40-0000GEO | Videoscape 3d model with gouraud curves | geo | Videoscape 3D, Blender | Carl
000001321-40-0000HRC | Softimage 4d model, binary encoded | hrc | Softimage 4D Creative environment | Carl
000001321-40-0000HRC | Softimage 4d model, ascii encoded | hrc | Softimage 4D Creative environment | Carl
000000000-40-000IGES | Initial Graphics Exchange Specification image file | iges,igs |  | Carl | NM
000001004-40-00000IV | Open Inventor 3d model | iv | Open Inventor Toolkit | Carl
000100118-40-000LIST | Geomview list of 3D models and objects | list | Geomview | Carl
000001254-40-00000LP | Lightscape 3d model | lp | Lightscape 3d | Carl | MP
000001251-40-0000LWO | Lightwave 3D object | lwo,lwob | Lightwave 3D | Carl
000001251-40-0000LWO | Lightwave 3D object | lwob,lwo | Lightwave 3D | Carl
000001251-40-0000LWS | Lightwave 3D scene | lwsc,lws | Lightwave 3D | Carl
000001312-40-00000MA | Maya 3d model, ascii encoded | ma | Maya | Carl
000001255-40-000MC4D | Maxon Cinema 4D v4.x 3D data | mc4d | Cinema 4D Version 4.x and earlier | Carl
000100118-40-000MESH | Geomview polygon | mesh | Geomview | Carl
000100118-40-000MESH | Geomview polygon | mesh | Geomview | Carl
000100112-40-0000MGF | Materials and Geometry format | mgf |  | Carl | NM
000100117-40-000MS3D | Milkshape 3d model, binary encoded | ms3d | Milshape 3d | Carl
000001329-40-000MSLD | Manchester Scene Description Language 3d model | msld |  | Carl | NM
000100109-40-0000NFF |  | nff |  | Carl | NM
000001253-40-0000NFF | Sense8 Worldtoolkit 3D object | nff | Worldtoolkit | Carl
000100119-40-0000NOB |  | nob,nsc | Now3D | Carl | MP
000001312-40-0000OBJ |  | obj | Wavefront Advanced visualiser | Carl | NM
000100113-40-0000OFF | Object File Format | off |  | Carl | NM
000100118-40-0000OFF | Geomview 3D model | off | Geomview | Carl | MP
000100118-40-0000OFF | Geomview 3D model | off | Geomview | Carl | MP
000001254-40-0000PLY | Autodesk animator polygon file | ply | Autodesk Animator | Carl
000001254-40-0000PLY | Autodesk animator polygon file | ply | Autodesk Animator | Carl
000001327-40-0000PLY | Stanford triangle format polygon model | ply |  | Carl | MP
000100108-40-0000POV |  | pov | Persistence of Vision™ Ray Tracer | Carl | NM
000001334-40-0000Q3O | Quick3d 3D object | q3o | Quick3d | Carl
000001334-40-0000Q3S | Quick3d 3D scene | q3s | Quick3d | Carl
000100110-40-0000QRT |  | qrt | Quick Ray Trace (QRT) | Carl | NM
000100118-40-000QUAD | Geomview polygon | quad | Geomview | Carl | MP
000100118-40-000QUAD | Geomview polygon | quad | Geomview | Carl | MP
000100118-40-000QUAD | Geomview polygon | quad | Geomview | Carl | MP
000100118-40-000QUAD | Geomview polygon | quad | Geomview | Carl | MP
000100112-40-0000RAD |  | rad | Radiance | Carl | NM
000100106-40-0000RAY |  | ray | Rayshade | Carl | NM
000001323-40-0000RIB | Renderman bytestream 3D model | rib | Renderman | Carl
000000000-40-00SCENE | Sculpt 3d scene model | scene | Sculpt 3d | Carl
000100118-40-000SKEL | Geomview polygons/vectors | skel | Geomview | Carl | MP
000001325-40-0000STL | Stereolithography 3d model, ascii encoded | stl | SLA CAD | Carl | MP
000001325-40-0000STL | Stereolithography 3d model, binary encoded | stl | SLA CAD | Carl | NM
000001252-40-000TDDD | Imagine 3D object | tddd,obj | Imagine 3D Studio, Turbo Silver | Carl
000100117-40-0000TXT | Milkshape 3d model, ascii encoded | txt | Milshape 3d | Carl | NM
000001004-40-0000TXT | Yet another description language | txt | Powerflip | Carl | NM
000001333-40-0000UDO |  | udo | MORAY | Carl | NEM
000100114-40-000000V |  | v | Vivid ray tracer | Carl | NM
000100118-40-000VECT | Geomview vector | vect | Geomview | Carl | MP
000001259-40-0000W3D | Shockwave 3D model | w3d | Macromedia Director | Carl
000000001-40-0014772 | Virtual Reality modeling language | wrl |  | Carl
000000001-40-0019776 | X3d 3d model | x3d |  | Carl | MP
000000000-40-0000XGL | XGL 3d model | xgl |  | Carl
000001001-40-0000XIE | Microsoft direct3d 3D model | xie | Direct3D | Carl
000001321-40-0000XSI | Softimage 3d model | xsi | Softimage XSI | Carl
000000000-50-0000000 |  |  | TurtleSmasher | Carl
000000000-50-0000000 |  |  | TWPack | Carl | NM
000000000-50-0000000 | Kboom archive file |  | Kaboom | Carl
000100077-50-0000000 | Context tree weighing (CTW) archive file |  | CTW | Carl
000100078-50-0000000 |  |  | Bicom | Carl | NM
000100080-50-0000000 |  |  | JCalc | Carl | MP
000001001-50-0000000 | Microsoft LZSS compressed file |  | Microsoft Compress | Carl
000001281-50-0000AAX | AAX archive file | aax | AAX | Carl
000001282-50-0000ABP | ABComp archive file | abp | ABComp | Carl
000100035-50-0000ACB |  | acb | ACB (Associative coder of Buyanovsky) | Carl
000001265-50-0000ACE | Ace / WinACE archive file | ace | Ace / WinAce | Carl
000000000-50-00000AI | Ai archive file | ai | Ai Archiver | Carl
000001283-50-0000AIN |  | ain | Ain archiver | Carl
000000000-50-0000AKT | AKT archive file | akt | Akt archiver | Carl
000001284-50-0000AMG | AMG archive file | amg | AMG Archiver | Carl
000000003-50-00000AR | UNIX archive file (ar) | ar | ar | Carl
000100036-50-0000AR7 | AR7 archive file | ar7 | AR7 | Carl
000001299-50-0000ARC |  | arc,pak | Arc archive | Carl | MP
000100037-50-0000ARG |  | arg | Arg | Carl | NM
000100038-50-0000ARH | Squash archive file | arh | Squash | Carl
000001285-50-0000ARJ | ARJ archive file | arj | Arj | Carl
000001286-50-0000ARQ |  | arq | Crusher! | Carl
000001287-50-0000ASD | ASD archive file | asd | ASD | Carl
000100040-50-0000B58 | BOA constrictor archive file | b58 | Boa constrictor | Carl
000100041-50-00000BA |  | ba | Ba (Burrows and Wheeler's transform) | Carl
000100042-50-00000BC | BWC archive file | bc | BWC | Carl
000100037-50-0000BIX | BIX archive file | bix | Bix | Carl
000001288-50-0000BLI |  | bli | Blink | Carl | NM
000100043-50-0000BOO | Btoa encoded file | boo | Btoa | Carl
000001289-50-0000BSN | Bsa archive file | bsn | Bsa | Carl
000100074-50-000BTPC | BTPC compressed image file | btpc | BTPC | Carl
000100044-50-0000BTS | BTSpk archive file | bts | BTS | Carl
000100008-50-00000BZ | Bzip archive file | bz | Bzip | Carl
000100008-50-0000BZ2 | Bzip2 archive file | bz2 | Bzip2 | Carl
000001001-50-0000CAB | Microsoft Cabinet file | cab |  | Carl
000001300-50-0000CPT |  | cpt | Compact Pro | Carl | MP
000001290-50-0000CRU | Crush archive file | cru | Crush | Carl
000100045-50-0000CXF | Ctx archive file | cxf | Ctxf | Carl
000000000-50-0000DAX | DAX audio archive file | dax | DAXWav | Carl
000000000-50-0000DEB |  | deb | Debpkg | Carl | MP
000000000-50-0000DMS | Diskmasher archive file | dms | Diskmasher | Carl
000100046-50-0000DPA | Dpae archive file | dpa | Dpae | Carl
000100047-50-0000DST | Disintegrator archive file | dst | Disintegrator | Carl
000100048-50-0000DUR |  | dur | Durilca | Carl
000100049-50-0000DWC |  | dwc | DWC | Carl
000100050-50-0000ELI |  | eli | ELI | Carl
000100051-50-0000ENC | Enhanced compressor archive file | enc | Enhanced compressor (ENC) | Carl
000100052-50-00000EN |  | eri | ERI | Carl | NM
000100002-50-0000ESP | ESP archive file | esp | ESP | Carl
000100002-50-0000EXE | ESP Self-extracting archivew (MS-DOS) | exe | ESP | Carl
000000000-50-000000F | Freeze archive file, version 1.0 | f | Freeze | Carl
000000000-50-000000F | Freeze archive file, version 2.0 | f | Freeze | Carl
000100055-50-00000GQ | Qlfc archive file | gq | Qlfc | Carl
000000002-50-0001952 | Gzip archive file | gz | Gzip | Carl
000100013-50-00000HA | HA archive file | ha | Ha | Carl
000001291-50-0000HAP | HAP archive file | hap | HAP | Carl
000100016-50-0000HPK | Hpack archive file | hpk | Hpack | Carl
000001002-50-0000HQX | BinHex archive | hqx |  | Carl
000100056-50-0000HYP | HYP archive file | hyp | HYP | Carl
000100056-50-0000HYP | HYP archive file | hyp | HYP | Carl
000100057-50-0000ICE |  | ice | ICE | Carl
000001270-50-0000IMP | Winimp archive file | imp | Winimp | Carl
000001011-50-0000JAR |  | jar | jar | Carl | MP
000001263-50-0000JRC | JRchive archive file | jrc | JRchive | Carl
000100001-50-00000LG | Arhangel archive file | lg | Archive Handler | Carl
000100003-50-0000LIM | Limit archive file | lim | Limit | Carl
000100017-50-0000LZH | Larc archive | lzh | Larc | Carl
000100017-50-0000LZH | Larc archive file | lzh | Larc | Carl
000100017-50-0000LZH | Larc archive file | lzh | Larc | Carl
000100017-50-0000LZH | LHarc archive file, version 2.x | lzh,lha | lha | Carl
000100017-50-0000LZH | LHarc archive file, version 1.x | lzh,lha | lha | Carl
000100017-50-0000LZH | LHarc archive file, version 1.x | lzh,lha | lha | Carl
000100017-50-0000LZH | LHarc archive file, version 2.x | lzh,lha | lha | Carl
000100017-50-0000LZH | LHarc archive file, version 2.x | lzh,lha | lha | Carl
000100017-50-0000LZH | LHarc archive file, version 2.x | lzh,lha | lha | Carl
000100017-50-0000LZH | LHarc archive file, version 2.x | lzh,lha | lha | Carl
000100017-50-0000LZH | LHarc archive file, version 2.x | lzh,lha | lha | Carl
000100017-50-0000LZH | LHarc archive file, version 2.x | lzh,lha | lha | Carl
000100017-50-0000LZH | LHarc archive file, version 2.x | lzh,lha | lha | Carl
000100037-50-000LZMA |  | lzma | Lzma SDK | Carl | NM
000100018-50-0000LZO | LZOP archive file | lzo | lzo | Carl
000100058-50-0000LZX | LZX archive file | lzx | Lzx | Carl
000100079-50-0000M99 |  | m99 | M99 | Carl | NM
000100004-50-00000MD | Mike Davenport archive file | md | Mdcd (Mike Davenport compressor) | Carl
000001292-50-0000NSK | NaShrink archive file | nsk | Nashrink | Carl
000100068-50-0000ONE | Semone archive file | one | Semone archiver | Carl
000001293-50-0000OOP |  | oop | OOP | Carl
000100084-50-0000PAC | LPAC audio archive file | pac | Lpac | Carl
000001262-50-0000PAC | CrossePAC archive file | pac | CrossePAC | Carl
000100060-50-0000PAQ |  | paq | Opaque | Carl
000001011-50-0000PKG |  | pkg | pkgmk | Carl | MP
000100061-50-0000PMZ | PPMZ2 archive file | pmz | High Compression Markov Predictive Coder | Carl
000100062-50-00000PP | Powerpacker archive file | pp | Powerpacker | Carl
000100064-50-0000PQ1 | PAQ1 archive file | pq1 | PAQ1 | Carl
000100064-50-0000PQ3 | PAQ3 archive file | pq3 | PAQ3 | Carl
000100064-50-0000PQ6 | PAQ6 archive file | pq6 | PAQ6 | Carl
000100065-50-0000PSA | Pretty simple archiver archive file | psa | Pretty simple archiver | Carl
000001294-50-000000Q | Quantum archive file | q | Quantum compressor | Carl
000001267-50-0000RAR | RAR archive file | rar | Rar | Carl
000001295-50-0000RAX | RAX archive file | rax | Romanian archiver eXpert (RAX) | Carl
000100066-50-0000RDQ | Reduq archive file | rdq | Reduq | Carl
000001296-50-00000RK |  | rk | RK Archiver | Carl
000000000-50-0000RPM | RPM archive | rpm | RPM | Carl
000100076-50-00000RZ | Rzip archive file | rz | rzip | Carl
000001264-50-0000SAR | Streaming Archiver Utility archive file | sar | Streamline Archival Utility | Carl
000001264-50-0000SAR | Streaming Archiver Utility archive file | sar | Streamline Archival Utility | Carl
000001264-50-0000SAR | Streaming Archiver Utility archive file | sar | Streamline Archival Utility | Carl
000001297-50-00000SB | SBX archive file | sb | SBX Archiver | Carl
000100067-50-0000SBC | SBC archive file | sbc | SBC Archiver | Carl
000000000-50-000SHAR | UNIX shell archive | shar |  | Carl
000000000-50-000SHAR | UNIX shell archive | shar |  | Carl
000100005-50-0000SHK | Shrinkit/Nulib archive file | shk | Nulib | Carl
000100005-50-0000SHK | Shrinkit/Nulib archive file | shk | Nulib | Carl
000001272-50-0000SIT | Stuffit archive file | sit | Stuffit | Carl
000001272-50-0000SIT | Stuffit archive file | sit | Stuffit | Carl
000001272-50-000SITX | Stuffit extended archive file | sitx | Stuffit Extended | Carl
000000000-50-0000SOF | SOF archive file | sof | Sof | Carl
000100006-50-0000SPL | Splint archive file | spl | Splint | Carl
000100014-50-0000SQZ | Sqwez archive file | sqz | Sqweez | Carl
000100015-50-0000SQZ | Squeeze archive file | sqz | Sqz | Carl
000100063-50-0000STC | Stonecracker archive file | stc | Stonecracker | Carl
000100063-50-0000STC | Stonecracker archive file | stc | Stonecracker | Carl
000100063-50-0000STC | Stonecracker archive file | stc | Stonecracker | Carl
000100009-50-00000SZ | SZIP archive file | sz | Szip | Carl
000000000-50-0000TAR | GNU tar archive | tar | Tar,pax | Carl
000000003-50-0001003 | Opengroup/POSIX tar archive | tar | Tar,pax | Carl
000000000-50-0000TVC |  | tvc | TVC | Carl
000001271-50-0000UC2 | Ultra Compressor archive file | uc2 | uc2 | Carl
000100083-50-0000UHA | UHArc archive file | uha | Uharc | Carl
000100082-50-00000WA |  | wa | Wavarc | Carl | MP
000100081-50-00000WV |  | wv | Wavpack | Carl | MP
000001301-50-00000WV |  | wv | SonArc | Carl | MP
000001298-50-0000XIE |  | xie | XIE Archiver | Carl
000100075-50-0000XPM |  | xpm | XMLppm | Carl
000001020-50-0000XPM |  | xpm | XMLppm | Carl
000100071-50-0000YBS | YBS archive file | ybs | YBS archiver | Carl
000100072-50-00000YC |  | yc | Yet Another Compressor (YAC) | Carl
000000000-50-000000Z | UNIX archive file | z |  | Carl
000100073-50-0000ZET |  | zet | ZET Archiver | Carl
000000000-50-0000ZIP |  | zip | DOS Package | Carl | MP
000100070-50-0000ZIP |  | zip | X1 archiver | Carl
000001266-50-0000ZIP | Pkzip archive file | zip | Pkunzip, Info-zip Unzip | Carl
000100012-50-0000ZOO | Zoo archive file | zoo | zoo | Carl
000000000-50-0000ZPK |  | zpk | Zeropacker | Carl | NM
000100007-50-00000ZZ | ZZip archive file | zz | Zzip | Carl
000100002-51-0000COM | 624 executable compressed file (MS-DOS) | com | 624 | Carl
000100002-51-0000COM | 624 executable compressed file (MS-DOS) | com | 624 | Carl
000100053-51-0000EXE | Lzexe compressed executable file (MS-DOS) | exe | Lzexe | Carl
000001001-60-0000CHM | Microsoft compiled hypertext document | chm | HTML Help Workshop | Carl
000001005-60-0000DDP | Delphi Diagram Portfolio file | ddp | Borland Delphi | Carl
000001268-60-0000DOC | Pagestream document | doc | Pagestream | Carl
000001010-60-000FTXT | Formatted text interchange file | ftxt |  | Carl
000001010-60-000FTXT | Formatted text interchange file | ftxt |  | Carl
000001010-60-000FTXT | Formatted text interchange file | ftxt |  | Carl
000001007-60-00GUIDE | AmigaGuide hypertext document | guide |  | Carl
000001001-60-0000HLP | Microsoft Windows Help file | hlp |  | Carl
000000001-60-0015445 | HyperText Markup Language document (HTML) | html,htm |  | Carl
000001006-60-0000HYP | Atari ST-Guide hypertext document | hyp |  | Carl
000001009-60-0000INF | OS/2 Guide hypertext document | inf | OS/2 | Carl
000100010-60-000INFO | GNU Info hypertext document | info |  | Carl
000000001-60-0015930 | Portable document format document file (PDF) | pdf | Adobe Acrobat | Carl
000001001-60-0000RTF | Rich Text Format document | rtf | Microsoft Wordpad | Carl
000000001-60-0008879 | Standard general markup language document (SGML) | sgml,sgm | DocBook | Carl
000001005-60-0000TCH | Turbo C help file | tch | Turbo C | Carl
000001005-60-0000TPH | Borland Pascal help file | tph | Turbo Pascal | Carl
000001005-60-0000TVH | Borland Turbo Vision help file | tvh | Turbo Vision | Carl
000001008-60-0000WPD | Wordperfect document | wpd,doc | Wordperfect | Carl
000001001-60-0000WRI | Microsoft Write document | wri | Microsoft Write | Carl
000001001-60-0000WRI | Microsoft Write document | wri | Microsoft Write | Carl
000001003-70-0000BDF | Adobe glyph bitmap distribution format font file | bdf | X-Windows | Carl
000001010-70-000000C | Deluxe paint multi-colour font file | c | Deluxe Paint | Carl
000100122-70-0000FLF | Figlet font file | flf | Figlet | Carl
000001336-70-0000LIB | Intellifont Scalable Typeface Format file | lib,type | PCL 5 | Carl
000001010-70-000000M | Deluxe paint mono colour font file | m | Deluxe Paint | Carl
000001001-70-0000TTF | Opentype font file | otf,ttf |  | Carl
000001001-70-0000TTF | Opentype font file, CFF type | otf,ttf |  | Carl
000000000-70-0000PCF | Portable compiled format (PCF) font file | pcf | X-Windows | Carl
000000001-70-0009541 | Type 1 font file | pfa |  | Carl
000000001-70-0009541 | Type 1 font file | pfa |  | Carl
000001003-70-0000PFB | Type 1 printer font binary file | pfb |  | Carl
000001003-70-0000PFB | Type 1 printer font binary file | pfb |  | Carl
000001337-70-0000SPD | Bitstream Speedo font file | spd | X-Windows, GemDOS | Carl
000000000-70-0000TFM | TeX Font metric data | tfm | Tex,Latex | Carl | NEM
000001002-70-0000TTF | Truetype font file | ttf |  | Carl
000001002-70-0000TTF | Truetype font file | ttf |  | Carl
000001003-70-0000AFM | Adobe composite font metrics file | afm |  | Carl
000001003-70-0000AFM | Adobe font metrics file | afm |  | Carl
000001003-70-0000AFM | Adobe master font metrics file | afm |  | Carl
000001001-70-0000PFM | Printer Font Metrics file for Type 1 fonts | pfm |  | Carl
000001001-81-0000ASF | Microsoft Advanced Streaming format multimedia file | asf,wma,wmv |  | Carl
000001001-81-0000AVI | Audio-video interleaved movie, little-endian | avi |  | Carl
000001001-81-0000AVI | Audio-video interleaved movie, big-endian | avi |  | Carl
000001002-81-0000MOV | Apple QuickTime movie data (mdat) | mov,qt | Quicktime | Carl
000001002-81-0000MOV | Apple QuickTime movie resource (moov) | mov,qt | Quicktime | Carl
000000001-81-000MPEG | MPEG multimedia (audio/video) stream file | mpe,mpeg,mpg |  | Carl
000000001-81-000MPEG | MPEG multimedia (audio/video) stream file | mpe,mpeg,mpg |  | Carl
000000001-81-000MPEG | MPEG multimedia (audio/video) stream file | mpe,mpeg,mpg |  | Carl
000001004-81-00000MV | Alias/Wavefront movie file | mv | Alias/Wavefront | Carl
000000000-81-0000OGG | OGG Multimedia container stream file | ogg |  | Carl
000001027-81-00000RM | RealMedia multimedia container stream file | rm,ra,rt,rp,rpa | Realplayer | Carl
000001259-81-0000SWF | Shockwave Macromedia animation | swf | Macromedia Flash | Carl
000000000-81-000VIVO | Vivo multimedia stream file | viv,vivo | Vivo player | Carl
000001261-82-000ANIM | Amiga / Sparta software animation | anim | Aegis Animator | Carl
000001260-82-000FANT | Fantavision movie | fant | Fantavision movie maker | Carl
000001254-82-0000FLC | Autodesk Animator Pro animation | flc | Autodesk Animator Pro | Carl
000001254-82-0000FLI | Autodesk Animator animation | fli | Autodesk Animator | Carl
000000000-82-0000MNG | Multi-image network graphics animation file | mng |  | Carl
000000000-82-0000SEQ | Cyberpaint Animation Sequence | seq | Cyberpaint | Carl
000000008-91-0000OFX | Open financial exchange file (XML) | ofx | Quicken,Money | Carl | MP
000000008-91-0000QFX | Open financial exchange file (SGML) | qfx | Quicken,Money | Carl
000001335-91-0000QIF | Quicken interchange file | qif | Quicken | Carl
000001335-91-0000QIF | Quicken interchange file | qif | Quicken | Carl
000001335-91-0000QIF | Quicken interchange file | qif | Quicken | Carl
000001335-91-0000QIF | Quicken interchange file | qif | Quicken | Carl
000001335-91-0000QIF | Quicken interchange file | qif | Quicken | Carl
000001335-91-0000QIF | Quicken interchange file | qif | Quicken | Carl
000001335-91-0000QIF | Quicken interchange file | qif | Quicken | Carl
000001335-91-0000QIF | Quicken interchange file | qif | Quicken | Carl
000001335-91-0000QIF | Quicken interchange file | qif | Quicken | Carl
000001335-91-0000QIF | Quicken interchange file | qif | Quicken | Carl
000001001-B0-0000CRD | Windows 3.x cardfile | crd |  | Carl
000001001-B0-0000CRD | Windows NT 3.51 card file | crd |  | Carl
000001015-B0-0000VCF | vCard Business Card file | vcf |  | Carl
000001001-B1-0000CAL | Microsoft windows calendar file | cal |  | Carl
000000002-B1-0002445 | iCalendar calendar file | ics,ifb |  | Carl
000001016-B1-0000VCS | vCalendar/iCalendar Agenda file | vcs |  | Carl
000001010-F0-0000IFF | Electronic Arts interchange file format | iff |  | Carl
000001001-F1-000RIFF | Microsoft Resource interchange file format | riff |  | Carl
000000007-F3-0000XML | Extensible Markup language (XML) file, UTF-32BE encoded | xml |  | Carl
000000007-F3-0000XML | Extensible Markup language (XML) file, UTF-32BE encoded | xml |  | Carl
000000007-F3-0000XML | Extensible Markup language (XML) file, UTF-16BE encoded | xml |  | Carl
000000007-F3-0000XML | Extensible Markup language (XML) file, UTF-32LE encoded | xml |  | Carl
000000007-F3-0000XML | Extensible Markup language (XML) file, UTF-16LE encoded | xml |  | Carl
000000007-F3-0000XML | Extensible Markup language (XML) file, UTF-8 encoded | xml |  | Carl
000000007-F3-0000XML | Extensible Markup language (XML) file, UTF-16BE encoded | xml |  | Carl
000000007-F3-0000XML | Extensible Markup language (XML) file, UTF-32LE encoded | xml |  | Carl
000000007-F3-0000XML | Extensible Markup language (XML) file, UTF-16LE encoded | xml |  | Carl
000000007-F3-0000XML | Extensible Markup language (XML) file | xml |  | Carl
000001001-F4-0000OLE | Microsoft OLE Compound file, big-endian | ole |  | Carl
000001001-F4-0000OLE | Microsoft OLE Compound file, little-endian | ole |  | Carl
000100120-11-0000PPU | Freepascal unit file | ppu,ppl,ppo,ppw,ppa,ppt | Freepascal compiler | Carl
000001011-10-0000EXP | Javacard API export file | exp | Smartcards | Carl
000100121-0F-0000IMG | Simple ROM filesystem (ROMFS) | img |  | Carl
000001001-0F-0000VHD | Virtual PC Hard drive | vhd | Virtual PC | Carl
000001003-33-00000PS | Postscript file | ps,eps |  | Carl Eric Codere
000001338-0F-0000ROM | eCos ROM Filesystem image (ROMFS) | rom,fs |  | Carl Eric Codere
000001339-A0-0000XML | Portable application description file (XML) | xml | PADGen | Carl Eric Codere
000001339-A0-0000XML | Portable application description file (XML) | xml | PADGen | Carl Eric Codere
000001003-A0-0000XMP | Extensible metadata platform sidecar file (XML) | xml,xmp |  | Carl Eric Codere
000001003-A0-0000XMP | Extensible metadata platform sidecar file (XML) | xml,xmp |  | Carl Eric Codere
000001340-00-000TEXI | Texinfo source file | texi | Texinfo | Carl Eric Codere
000001001-70-0000CPI | MS-DOS code page raster font | cpi | MS-DOS | Carl Eric Codere
000000000-70-0000VF1 | Berkeley vfont data | vf1,vf2 |  | Carl Eric Codere | NEM
000000000-90-0000000 | Timezone information database file (compiled) |  | UNIX | Carl Eric Codere
000100126-B0-0000FON | Telix phone book | fon | Telix | Carl Eric Codere
000001001-90-0000PCH | Microsoft Visual C++ pre-compiled header(s) | pch | Microsoft Visual C++ | Carl Eric Codere
000001001-90-0000PDB | Microsoft Visual C++ debug information database | pdb | Microsoft Visual C++ | Carl Eric Codere
000001001-90-0000ILK | Microsoft Visual C++ linker database | ilk | Microsoft Visual C++ | Carl Eric Codere

## Sheet1
Feature | Behavior | Notes
language detection | current language options exists only for the UI elements (English, German, Chinese). One can add a string statement in any language. The language tag is not captured in the "History", however, it does exist in the "source" | Current list: en, fr, de, nl, es, it, cn, ka, ru … all but "cn" isn't really a language code