## Issues Log
1 | Task | Description | Assigned To | Time Estimate (days) | Priority | Status | Comments
| admin/ project background | Background on CDL and UDFR project history; admin |  | 1 | 10 | In progress
| Set up VM | Set-up vm development environment + mercurial |  | 2 | 10
| Set up data stores/ontowiki | Set-up Virtuoso + OntoWiki |  | 2 | 10
| Test OntoWiki functionality | Test Ontowiki Built-in Functionality to establish gap |  | 3 | 10
| Create login/ auth | Authenticate Users. One role: editor. Potentially a second role: admin |  | 2 | 10
| Add validation to entities | Validation checking when saving |  | 2 | 50
| Validation display | Display validation errors to users |  | 2 | 50
| Roll-back | If a System error has occurred, the web interface shall roll back all data insertion to the registry.
|  |  | total | 14

## July 15
| VM and Environement Set-up | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days Developer | Completed Task Days Lisa | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2011-07-06 | [5 empty] | 0 | 5.6 | 11 | 0 |  | 0 | 0 |  | Independence | 2011-07-04 | 2026-07-29
| End Date | 2011-07-15 |  |  |  |  | 2011-07-06 | 1 | 4.9 | 10 | 1 | 0 | 1 | 1 | 1 | Labour Day | 2011-09-05
| # of Developers | 1 |  |  |  |  | 2011-07-07 | 2 | 4.2 | 9 | 1 | 0 | 2 | 2 | 1 | Veteran's Day | 2011-11-11
| Efficiency Factor | 0.7 |  |  |  |  | 2011-07-08 | 3 | 3.5 | 8 | 1 | 0 | 3 | 3 | 1 | Thanksgiving | 2011-11-24
| Work Days Total | 8 |  |  |  |  | 2011-07-11 | 4 | 2.8 | 7 | 1 | 0 | 4 | 4 | 1 | Thanks2 | 2011-11-25
| Dev Days Total | 8 |  |  |  |  | 2011-07-12 | 5 | 2.1 | 6 | 1 | 0 | 5 | 5 | 1 | Winter Holiday | 2011-12-26
| # of Task Work Days | 5.6 |  |  |  |  | 2011-07-13 | 6 | 1.4 | 5 | 1 | 0 | 6 | 6 | 1 | Winter2 | 2011-12-17
| m - Ideal Task Days Left | -0.7 |  |  |  |  | 2011-07-14 | 7 | 0.7 | 4 | 1 | 0 | 7 | 7 | 1 | New Year | 2011-12-30
| b - Ideal Task Days Left | 5.6 |  |  |  |  | 2011-07-15 | 8 | 0 | 3 | 1 | 0 | 8 | 8 | 1 | New Year2 | 2012-01-02
| m - Dev Days Used | 1
| b - Dev Days Used | 0
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status
| admin/ project background | 1 | complete
| Set up VM | 2 | Desktop has Ubuntu+MySQL. VM has Virtuoso Store running on dev machine | #N/A | #N/A | #N/A
| Set up data stores/ontowiki | 2 | complete | #N/A | #N/A | #N/A
| Test OntoWiki functionality | 3 | in progress | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
Testing, create svn tag, build release
| Total Tasks Assigned | 4
| Available Time - Assigned time | 11
-5.4
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),U2:U95)
Note on A14: Add the task ID's below

## Aug 1
| Authorization / Roles | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days Developer | Completed Task Days Lisa | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2011-07-18 | [10 empty] | 0 | 0 |  | Independence | 2011-07-04 | 2026-07-29
| End Date | 2011-08-01 |  |  |  |  | 2011-07-18 | 1 | 10 | 10 | 1 | 0 | 1 | 1 | 1 | Labour Day | 2011-09-05
| # of Developers | 1 |  |  |  |  | 2011-07-19 | 2 | 9 | 9 | 1 | 0 | 2 | 2 | 1 | Veteran's Day | 2011-11-11
| Efficiency Factor | 1 |  |  |  |  | 2011-07-21 | 3 | 8 | 8 | 1 | 0 | 3 | 3 | 1 | Thanksgiving | 2011-11-24
| Work Days Total | 10 |  |  |  |  | 2011-07-22 | 4 | 7 | 7 | 1 | 0 | 4 | 4 | 1 | Thanks2 | 2011-11-25
| Dev Days Total | 10 |  |  |  |  | 2011-07-25 | 5 | 6 | 6 | 1 | 0 | 5 | 5 | 1 | Winter Holiday | 2011-12-26
| # of Task Work Days | 10 |  |  |  |  | 2011-07-26 | 6 | 5 | 5 | 0 | 0 | 5 | 6 | 0.83 | Winter2 | 2011-12-17
| m - Ideal Task Days Left | -1 |  |  |  |  | 2011-07-27 | 7 | 4 | 5 | 0 | 0 | 5 | 7 | 0.71 | New Year | 2011-12-30
| b - Ideal Task Days Left | 10 |  |  |  |  | 2011-07-28 | 8 | 3 | 5 | 0 | 0 | 5 | 8 | 0.63 | New Year2 | 2012-01-02
| m - Dev Days Used | 1 |  |  |  |  | 2011-07-29 | 9 | 2 | 5 | 0 | 0 | 5 | 9 | 0.56 | Abhishek-out | 2011-07-20
| b - Dev Days Used | 0 |  |  |  |  | 2011-08-01 | 10 | 1 | 5 | 0 | 0 | 5 | 10 | 0.5
[7 empty] | 2011-08-02 | 11 | 0 | 5 | 0 | 0 | 5 | 11 | 0.45
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status
| Restrict Anonymous Login. | 1 | done
| Capture additional information upon account creation, | 1
| Contributor role: restrict edit of class resources; | 1 | done | #N/A | #N/A | #N/A
| Have Captcha for self-service | 1
| Disable for all - delete KB resource. Disable for all (but admin) delete KB | 2 | done | #N/A | #N/A | #N/A
| Create User Profile for Audit "History" | 1 |  | #N/A | #N/A | #N/A
| Create Editor Role - allow edit of Controlled Vocabulary | 1 |  | #N/A | #N/A | #N/A
| Create Reviewer Role - allow approval flags - to be created per resource (instance) - but shown per statement (in Audit History window) | 1 |  | #N/A | #N/A | #N/A
| Admin - assign user roles | 1 | done | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
Testing, create svn tag, build release
| Total Tasks Assigned | 4
| Available Time - Assigned time | 12
-2
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),U2:U97)
Note on A14: Add the task ID's below

## Aug 12
| Validation/Controlled Vocabulary Restrictions / Inferencing / Erfurt | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days John | Completed Task Days Sue | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2011-08-02 | [5 empty] | 0 | 6.3 | 4 |  |  |  |  | 0 | 0 |  | Independence | 2011-07-04 | 2026-07-29
| End Date | 2011-08-12 |  |  |  |  | 2011-08-02 | 1 | 5.6 | 4 | 0 | 0 |  |  | 0 | 1 | 0 | Labour Day | 2011-09-05
| # of Developers | 1 |  |  |  |  | 2011-08-03 | 2 | 4.9 | 3.5 | 0 | 0.5 |  |  | 0.5 | 2 | 0.25 | Veteran's Day | 2011-11-11
| Efficiency Factor | 0.7 |  |  |  |  | 2011-08-04 | 3 | 4.2 | 1.5 | 2 | 0 |  |  | 2.5 | 3 | 0.83 | Thanksgiving | 2011-11-24
| Work Days Total | 9 |  |  |  |  | 2011-08-05 | 4 | 3.5 | 1.5 | 0 | 0 |  |  | 2.5 | 4 | 0.63 | Thanks2 | 2011-11-25
| Dev Days Total | 9 |  |  |  |  | 2011-08-08 | 5 | 2.8 | 0.5 | 0 | 1 |  |  | 3.5 | 5 | 0.7 | Winter Holiday | 2011-12-26
| # of Task Work Days | 6.3 |  |  |  |  | 2011-08-09 | 6 | 2.1 | -2.5 | 0 | 3 |  |  | 6.5 | 6 | 1.08 | Winter2 | 2011-12-17
| m - Ideal Task Days Left | -0.7 |  |  |  |  | 2011-08-10 | 7 | 1.4 | -7 | 4.5 | 0 |  |  | 11 | 7 | 1.57 | New Year | 2011-12-30
| b - Ideal Task Days Left | 6.3 |  |  |  |  | 2011-08-11 | 8 | 0.7 | -8 | 0 | 1 |  |  | 12 | 8 | 1.5 | New Year2 | 2012-01-02
| m - Dev Days Used | 1 |  |  |  |  | 2011-08-12 | 9 | 0 | -11 | 2 | 1 |  |  | 15 | 9 | 1.67
| b - Dev Days Used | 0 |  |  |  |  | 2011-08-15 | 10 | -0.7 | -12 | 1 | 0 |  |  | 16 | 10 | 1.6
[7 empty] | 2011-08-16 | 11 | -1.4 | -14 | 0 | 2 |  |  | 18 | 11 | 1.64
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status
3 |  |  |  | #N/A | #N/A | #N/A
7 |  |  |  | #N/A | #N/A | #N/A
8 |  |  |  | #N/A | #N/A | #N/A
5 |  |  |  | #N/A | #N/A | #N/A
1 |  |  |  | #N/A | #N/A | #N/A
13 |  |  |  | #N/A | #N/A | #N/A
9 |  |  |  | #N/A | #N/A | #N/A
12 |  |  |  | #N/A | #N/A | #N/A
6 |  |  |  | #N/A | #N/A | #N/A
10 |  |  |  | #N/A | #N/A | #N/A
11 |  |  |  | #N/A | #N/A | #N/A
2 |  |  |  | #N/A | #N/A | #N/A
14 |  |  |  | #N/A | #N/A | #N/A
15 |  |  |  | #N/A | #N/A | #N/A
4 |  |  |  | #N/A | #N/A | #N/A
16 |  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
| Testing, create svn tag, build release | 4
| Total Tasks Assigned | 4
| Available Time - Assigned time | 2.3
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),W2:W94)
Note on A14: Add the task ID's below

## Aug 26
| Validation/Controlled Vocabulary Restrictions / Inferencing / Erfurt | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days John | Completed Task Days Sue | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2011-08-13 | [5 empty] | 0 | 7 | 4 |  |  |  |  | 0 | 0 |  | Independence | 2011-07-04 | 2026-07-29
| End Date | 2011-08-26 |  |  |  |  | 2011-08-13 | 1 | 6.3 | 4 | 0 | 0 |  |  | 0 | 1 | 0 | Labour Day | 2011-09-05
| # of Developers | 1 |  |  |  |  | 2011-08-15 | 2 | 5.6 | 3.5 | 0 | 0.5 |  |  | 0.5 | 2 | 0.25 | Veteran's Day | 2011-11-11
| Efficiency Factor | 0.7 |  |  |  |  | 2011-08-16 | 3 | 4.9 | 1.5 | 2 | 0 |  |  | 2.5 | 3 | 0.83 | Thanksgiving | 2011-11-24
| Work Days Total | 10 |  |  |  |  | 2011-08-17 | 4 | 4.2 | 1.5 | 0 | 0 |  |  | 2.5 | 4 | 0.63 | Thanks2 | 2011-11-25
| Dev Days Total | 10 |  |  |  |  | 2011-08-18 | 5 | 3.5 | 0.5 | 0 | 1 |  |  | 3.5 | 5 | 0.7 | Winter Holiday | 2011-12-26
| # of Task Work Days | 7 |  |  |  |  | 2011-08-19 | 6 | 2.8 | -2.5 | 0 | 3 |  |  | 6.5 | 6 | 1.08 | Winter2 | 2011-12-17
| m - Ideal Task Days Left | -0.7 |  |  |  |  | 2011-08-22 | 7 | 2.1 | -7 | 4.5 | 0 |  |  | 11 | 7 | 1.57 | New Year | 2011-12-30
| b - Ideal Task Days Left | 7 |  |  |  |  | 2011-08-23 | 8 | 1.4 | -8 | 0 | 1 |  |  | 12 | 8 | 1.5 | New Year2 | 2012-01-02
| m - Dev Days Used | 1 |  |  |  |  | 2011-08-24 | 9 | 0.7 | -11 | 2 | 1 |  |  | 15 | 9 | 1.67
| b - Dev Days Used | 0 |  |  |  |  | 2011-08-25 | 10 | 0 | -12 | 1 | 0 |  |  | 16 | 10 | 1.6
[7 empty] | 2011-08-26 | 11 | -0.7 | -14 | 0 | 2 |  |  | 18 | 11 | 1.64
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status | 2011-08-29 | 12 | -1.4 | -15 | 0 | 1 |  |  | 19 | 12 | 1.58
3 |  |  |  | #N/A | #N/A | #N/A | 2011-08-30 | 13 | -2.1 | -15 |  |  |  |  | 19 | 13 | 1.46
7 |  |  |  | #N/A | #N/A | #N/A
8 |  |  |  | #N/A | #N/A | #N/A
5 |  |  |  | #N/A | #N/A | #N/A
1 |  |  |  | #N/A | #N/A | #N/A
13 |  |  |  | #N/A | #N/A | #N/A
9 |  |  |  | #N/A | #N/A | #N/A
12 |  |  |  | #N/A | #N/A | #N/A
6 |  |  |  | #N/A | #N/A | #N/A
10 |  |  |  | #N/A | #N/A | #N/A
11 |  |  |  | #N/A | #N/A | #N/A
2 |  |  |  | #N/A | #N/A | #N/A
14 |  |  |  | #N/A | #N/A | #N/A
15 |  |  |  | #N/A | #N/A | #N/A
4 |  |  |  | #N/A | #N/A | #N/A
16 |  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
| Testing, create svn tag, build release | 4
| Total Tasks Assigned | 4
| Available Time - Assigned time | 3
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),W2:W94)
Note on A14: Add the task ID's below

## Sept 9
| Identifiers | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days John | Completed Task Days Sue | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2011-08-27 | [5 empty] | 0 | 6.3 | 4 |  |  |  |  | 0 | 0 |  | Independence | 2011-07-04 | 2026-07-29
| End Date | 2011-09-09 |  |  |  |  | 2011-08-27 | 1 | 5.6 | 4 | 0 | 0 |  |  | 0 | 1 | 0 | Labour Day | 2011-09-05
| # of Developers | 1 |  |  |  |  | 2011-08-29 | 2 | 4.9 | 3.5 | 0 | 0.5 |  |  | 0.5 | 2 | 0.25 | Veteran's Day | 2011-11-11
| Efficiency Factor | 0.7 |  |  |  |  | 2011-08-30 | 3 | 4.2 | 1.5 | 2 | 0 |  |  | 2.5 | 3 | 0.83 | Thanksgiving | 2011-11-24
| Work Days Total | 9 |  |  |  |  | 2011-08-31 | 4 | 3.5 | 1.5 | 0 | 0 |  |  | 2.5 | 4 | 0.63 | Thanks2 | 2011-11-25
| Dev Days Total | 9 |  |  |  |  | 2011-09-01 | 5 | 2.8 | 0.5 | 0 | 1 |  |  | 3.5 | 5 | 0.7 | Winter Holiday | 2011-12-26
| # of Task Work Days | 6.3 |  |  |  |  | 2011-09-02 | 6 | 2.1 | -2.5 | 0 | 3 |  |  | 6.5 | 6 | 1.08 | Winter2 | 2011-12-17
| m - Ideal Task Days Left | -0.7 |  |  |  |  | 2011-09-06 | 7 | 1.4 | -7 | 4.5 | 0 |  |  | 11 | 7 | 1.57 | New Year | 2011-12-30
| b - Ideal Task Days Left | 6.3 |  |  |  |  | 2011-09-07 | 8 | 0.7 | -8 | 0 | 1 |  |  | 12 | 8 | 1.5 | New Year2 | 2012-01-02
| m - Dev Days Used | 1 |  |  |  |  | 2011-09-08 | 9 | 0 | -11 | 2 | 1 |  |  | 15 | 9 | 1.67
| b - Dev Days Used | 0 |  |  |  |  | 2011-09-09 | 10 | -0.7 | -12 | 1 | 0 |  |  | 16 | 10 | 1.6
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status
3 |  |  |  | #N/A | #N/A | #N/A
7 |  |  |  | #N/A | #N/A | #N/A
8 |  |  |  | #N/A | #N/A | #N/A
5 |  |  |  | #N/A | #N/A | #N/A
1 |  |  |  | #N/A | #N/A | #N/A
13 |  |  |  | #N/A | #N/A | #N/A
9 |  |  |  | #N/A | #N/A | #N/A
12 |  |  |  | #N/A | #N/A | #N/A
6 |  |  |  | #N/A | #N/A | #N/A
10 |  |  |  | #N/A | #N/A | #N/A
11 |  |  |  | #N/A | #N/A | #N/A
2 |  |  |  | #N/A | #N/A | #N/A
14 |  |  |  | #N/A | #N/A | #N/A
15 |  |  |  | #N/A | #N/A | #N/A
4 |  |  |  | #N/A | #N/A | #N/A
16 |  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
| Testing, create svn tag, build release | 4
| Total Tasks Assigned | 4
| Available Time - Assigned time | 2.3
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),W2:W94)
Note on A14: Add the task ID's below

## Sept 23
| CMS | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days John | Completed Task Days Sue | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2011-09-10 | [5 empty] | 0 | 7 | 4 |  |  |  |  | 0 | 0 |  | Independence | 2011-07-04 | 2026-07-29
| End Date | 2011-09-23 |  |  |  |  | 2011-09-10 | 1 | 6.3 | 4 | 0 | 0 |  |  | 0 | 1 | 0 | Labour Day | 2011-09-05
| # of Developers | 1 |  |  |  |  | 2011-09-12 | 2 | 5.6 | 3.5 | 0 | 0.5 |  |  | 0.5 | 2 | 0.25 | Veteran's Day | 2011-11-11
| Efficiency Factor | 0.7 |  |  |  |  | 2011-09-13 | 3 | 4.9 | 1.5 | 2 | 0 |  |  | 2.5 | 3 | 0.83 | Thanksgiving | 2011-11-24
| Work Days Total | 10 |  |  |  |  | 2011-09-14 | 4 | 4.2 | 1.5 | 0 | 0 |  |  | 2.5 | 4 | 0.63 | Thanks2 | 2011-11-25
| Dev Days Total | 10 |  |  |  |  | 2011-09-15 | 5 | 3.5 | 0.5 | 0 | 1 |  |  | 3.5 | 5 | 0.7 | Winter Holiday | 2011-12-26
| # of Task Work Days | 7 |  |  |  |  | 2011-09-16 | 6 | 2.8 | -2.5 | 0 | 3 |  |  | 6.5 | 6 | 1.08 | Winter2 | 2011-12-17
| m - Ideal Task Days Left | -0.7 |  |  |  |  | 2011-09-19 | 7 | 2.1 | -7 | 4.5 | 0 |  |  | 11 | 7 | 1.57 | New Year | 2011-12-30
| b - Ideal Task Days Left | 7 |  |  |  |  | 2011-09-20 | 8 | 1.4 | -8 | 0 | 1 |  |  | 12 | 8 | 1.5 | New Year2 | 2012-01-02
| m - Dev Days Used | 1 |  |  |  |  | 2011-09-21 | 9 | 0.7 | -11 | 2 | 1 |  |  | 15 | 9 | 1.67
| b - Dev Days Used | 0 |  |  |  |  | 2011-09-22 | 10 | 0 | -12 | 1 | 0 |  |  | 16 | 10 | 1.6
[7 empty] | 2011-09-23 | 11 | -0.7 | -14 | 0 | 2 |  |  | 18 | 11 | 1.64
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status | 2011-09-26 | 12 | -1.4 | -15 | 0 | 1 |  |  | 19 | 12 | 1.58
3 |  |  |  | #N/A | #N/A | #N/A
7 |  |  |  | #N/A | #N/A | #N/A
8 |  |  |  | #N/A | #N/A | #N/A
5 |  |  |  | #N/A | #N/A | #N/A
1 |  |  |  | #N/A | #N/A | #N/A
13 |  |  |  | #N/A | #N/A | #N/A
9 |  |  |  | #N/A | #N/A | #N/A
12 |  |  |  | #N/A | #N/A | #N/A
6 |  |  |  | #N/A | #N/A | #N/A
10 |  |  |  | #N/A | #N/A | #N/A
11 |  |  |  | #N/A | #N/A | #N/A
2 |  |  |  | #N/A | #N/A | #N/A
14 |  |  |  | #N/A | #N/A | #N/A
15 |  |  |  | #N/A | #N/A | #N/A
4 |  |  |  | #N/A | #N/A | #N/A
16 |  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
| Testing, create svn tag, build release | 4
| Total Tasks Assigned | 4
| Available Time - Assigned time | 3
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),W2:W94)
Note on A14: Add the task ID's below

## Oct 7
| Web Services/ PRONOM load | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days John | Completed Task Days Sue | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2011-09-24 | [5 empty] | 0 | 7 | 4 |  |  |  |  | 0 | 0 |  | Independence | 2011-07-04 | 2026-07-29
| End Date | 2011-10-07 |  |  |  |  | 2011-09-24 | 1 | 6.3 | 4 | 0 | 0 |  |  | 0 | 1 | 0 | Labour Day | 2011-09-05
| # of Developers | 1 |  |  |  |  | 2011-09-26 | 2 | 5.6 | 3.5 | 0 | 0.5 |  |  | 0.5 | 2 | 0.25 | Veteran's Day | 2011-11-11
| Efficiency Factor | 0.7 |  |  |  |  | 2011-09-27 | 3 | 4.9 | 1.5 | 2 | 0 |  |  | 2.5 | 3 | 0.83 | Thanksgiving | 2011-11-24
| Work Days Total | 10 |  |  |  |  | 2011-09-28 | 4 | 4.2 | 1.5 | 0 | 0 |  |  | 2.5 | 4 | 0.63 | Thanks2 | 2011-11-25
| Dev Days Total | 10 |  |  |  |  | 2011-09-29 | 5 | 3.5 | 0.5 | 0 | 1 |  |  | 3.5 | 5 | 0.7 | Winter Holiday | 2011-12-26
| # of Task Work Days | 7 |  |  |  |  | 2011-09-30 | 6 | 2.8 | -2.5 | 0 | 3 |  |  | 6.5 | 6 | 1.08 | Winter2 | 2011-12-17
| m - Ideal Task Days Left | -0.7 |  |  |  |  | 2011-10-03 | 7 | 2.1 | -7 | 4.5 | 0 |  |  | 11 | 7 | 1.57 | New Year | 2011-12-30
| b - Ideal Task Days Left | 7 |  |  |  |  | 2011-10-04 | 8 | 1.4 | -8 | 0 | 1 |  |  | 12 | 8 | 1.5 | New Year2 | 2012-01-02
| m - Dev Days Used | 1 |  |  |  |  | 2011-10-05 | 9 | 0.7 | -11 | 2 | 1 |  |  | 15 | 9 | 1.67
| b - Dev Days Used | 0 |  |  |  |  | 2011-10-06 | 10 | 0 | -12 | 1 | 0 |  |  | 16 | 10 | 1.6
[7 empty] | 2011-10-07 | 11 | -0.7 | -14 | 0 | 2 |  |  | 18 | 11 | 1.64
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status
3 |  |  |  | #N/A | #N/A | #N/A
7 |  |  |  | #N/A | #N/A | #N/A
8 |  |  |  | #N/A | #N/A | #N/A
5 |  |  |  | #N/A | #N/A | #N/A
1 |  |  |  | #N/A | #N/A | #N/A
13 |  |  |  | #N/A | #N/A | #N/A
9 |  |  |  | #N/A | #N/A | #N/A
12 |  |  |  | #N/A | #N/A | #N/A
6 |  |  |  | #N/A | #N/A | #N/A
10 |  |  |  | #N/A | #N/A | #N/A
11 |  |  |  | #N/A | #N/A | #N/A
2 |  |  |  | #N/A | #N/A | #N/A
14 |  |  |  | #N/A | #N/A | #N/A
15 |  |  |  | #N/A | #N/A | #N/A
4 |  |  |  | #N/A | #N/A | #N/A
16 |  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
| Testing, create svn tag, build release | 4
| Total Tasks Assigned | 4
| Available Time - Assigned time | 3
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),W2:W94)
Note on A14: Add the task ID's below

## Oct 21
| Facets / Search | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days John | Completed Task Days Sue | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2011-10-08 | [5 empty] | 0 | 7 | 4 |  |  |  |  | 0 | 0 |  | Independence | 2011-07-04 | 2026-07-29
| End Date | 2011-10-21 |  |  |  |  | 2011-10-08 | 1 | 6.3 | 4 | 0 | 0 |  |  | 0 | 1 | 0 | Labour Day | 2011-09-05
| # of Developers | 1 |  |  |  |  | 2011-10-10 | 2 | 5.6 | 3.5 | 0 | 0.5 |  |  | 0.5 | 2 | 0.25 | Veteran's Day | 2011-11-11
| Efficiency Factor | 0.7 |  |  |  |  | 2011-10-11 | 3 | 4.9 | 1.5 | 2 | 0 |  |  | 2.5 | 3 | 0.83 | Thanksgiving | 2011-11-24
| Work Days Total | 10 |  |  |  |  | 2011-10-12 | 4 | 4.2 | 1.5 | 0 | 0 |  |  | 2.5 | 4 | 0.63 | Thanks2 | 2011-11-25
| Dev Days Total | 10 |  |  |  |  | 2011-10-13 | 5 | 3.5 | 0.5 | 0 | 1 |  |  | 3.5 | 5 | 0.7 | Winter Holiday | 2011-12-26
| # of Task Work Days | 7 |  |  |  |  | 2011-10-14 | 6 | 2.8 | -2.5 | 0 | 3 |  |  | 6.5 | 6 | 1.08 | Winter2 | 2011-12-17
| m - Ideal Task Days Left | -0.7 |  |  |  |  | 2011-10-17 | 7 | 2.1 | -7 | 4.5 | 0 |  |  | 11 | 7 | 1.57 | New Year | 2011-12-30
| b - Ideal Task Days Left | 7 |  |  |  |  | 2011-10-18 | 8 | 1.4 | -8 | 0 | 1 |  |  | 12 | 8 | 1.5 | New Year2 | 2012-01-02
| m - Dev Days Used | 1 |  |  |  |  | 2011-10-19 | 9 | 0.7 | -11 | 2 | 1 |  |  | 15 | 9 | 1.67
| b - Dev Days Used | 0 |  |  |  |  | 2011-10-20 | 10 | 0 | -12 | 1 | 0 |  |  | 16 | 10 | 1.6
[7 empty] | 2011-10-21 | 11 | -0.7 | -14 | 0 | 2 |  |  | 18 | 11 | 1.64
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status | 2011-10-24 | 12 | -1.4 | -15 | 0 | 1 |  |  | 19 | 12 | 1.58
3 |  |  |  | #N/A | #N/A | #N/A
7 |  |  |  | #N/A | #N/A | #N/A
8 |  |  |  | #N/A | #N/A | #N/A
5 |  |  |  | #N/A | #N/A | #N/A
1 |  |  |  | #N/A | #N/A | #N/A
13 |  |  |  | #N/A | #N/A | #N/A
9 |  |  |  | #N/A | #N/A | #N/A
12 |  |  |  | #N/A | #N/A | #N/A
6 |  |  |  | #N/A | #N/A | #N/A
10 |  |  |  | #N/A | #N/A | #N/A
11 |  |  |  | #N/A | #N/A | #N/A
2 |  |  |  | #N/A | #N/A | #N/A
14 |  |  |  | #N/A | #N/A | #N/A
15 |  |  |  | #N/A | #N/A | #N/A
4 |  |  |  | #N/A | #N/A | #N/A
16 |  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
| Testing, create svn tag, build release | 4
| Total Tasks Assigned | 4
| Available Time - Assigned time | 3
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),W2:W94)
Note on A14: Add the task ID's below

## Nov 4
| Overflow | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days John | Completed Task Days Sue | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2011-10-22 | [5 empty] | 0 | 7 | 4 |  |  |  |  | 0 | 0 |  | Independence | 2011-07-04 | 2026-07-29
| End Date | 2011-11-04 |  |  |  |  | 2011-10-22 | 1 | 6.3 | 4 | 0 | 0 |  |  | 0 | 1 | 0 | Labour Day | 2011-09-05
| # of Developers | 1 |  |  |  |  | 2011-10-24 | 2 | 5.6 | 3.5 | 0 | 0.5 |  |  | 0.5 | 2 | 0.25 | Veteran's Day | 2011-11-11
| Efficiency Factor | 0.7 |  |  |  |  | 2011-10-25 | 3 | 4.9 | 1.5 | 2 | 0 |  |  | 2.5 | 3 | 0.83 | Thanksgiving | 2011-11-24
| Work Days Total | 10 |  |  |  |  | 2011-10-26 | 4 | 4.2 | 1.5 | 0 | 0 |  |  | 2.5 | 4 | 0.63 | Thanks2 | 2011-11-25
| Dev Days Total | 10 |  |  |  |  | 2011-10-27 | 5 | 3.5 | 0.5 | 0 | 1 |  |  | 3.5 | 5 | 0.7 | Winter Holiday | 2011-12-26
| # of Task Work Days | 7 |  |  |  |  | 2011-10-28 | 6 | 2.8 | -2.5 | 0 | 3 |  |  | 6.5 | 6 | 1.08 | Winter2 | 2011-12-17
| m - Ideal Task Days Left | -0.7 |  |  |  |  | 2011-10-31 | 7 | 2.1 | -7 | 4.5 | 0 |  |  | 11 | 7 | 1.57 | New Year | 2011-12-30
| b - Ideal Task Days Left | 7 |  |  |  |  | 2011-11-01 | 8 | 1.4 | -8 | 0 | 1 |  |  | 12 | 8 | 1.5 | New Year2 | 2012-01-02
| m - Dev Days Used | 1 |  |  |  |  | 2011-11-02 | 9 | 0.7 | -11 | 2 | 1 |  |  | 15 | 9 | 1.67
| b - Dev Days Used | 0 |  |  |  |  | 2011-11-03 | 10 | 0 | -12 | 1 | 0 |  |  | 16 | 10 | 1.6
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status
3 |  |  |  | #N/A | #N/A | #N/A
7 |  |  |  | #N/A | #N/A | #N/A
8 |  |  |  | #N/A | #N/A | #N/A
5 |  |  |  | #N/A | #N/A | #N/A
1 |  |  |  | #N/A | #N/A | #N/A
13 |  |  |  | #N/A | #N/A | #N/A
9 |  |  |  | #N/A | #N/A | #N/A
12 |  |  |  | #N/A | #N/A | #N/A
6 |  |  |  | #N/A | #N/A | #N/A
10 |  |  |  | #N/A | #N/A | #N/A
11 |  |  |  | #N/A | #N/A | #N/A
2 |  |  |  | #N/A | #N/A | #N/A
14 |  |  |  | #N/A | #N/A | #N/A
15 |  |  |  | #N/A | #N/A | #N/A
4 |  |  |  | #N/A | #N/A | #N/A
16 |  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
| Testing, create svn tag, build release | 4
| Total Tasks Assigned | 4
| Available Time - Assigned time | 3
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),W2:W94)
Note on A14: Add the task ID's below

## Nov 18
| Overflow | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days John | Completed Task Days Sue | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2011-11-05 | [5 empty] | 0 | 6.3 | 4 |  |  |  |  | 0 | 0 |  | Independence | 2011-07-04 | 2026-07-29
| End Date | 2011-11-18 |  |  |  |  | 2011-11-05 | 1 | 5.6 | 4 | 0 | 0 |  |  | 0 | 1 | 0 | Labour Day | 2011-09-05
| # of Developers | 1 |  |  |  |  | 2011-11-07 | 2 | 4.9 | 3.5 | 0 | 0.5 |  |  | 0.5 | 2 | 0.25 | Veteran's Day | 2011-11-11
| Efficiency Factor | 0.7 |  |  |  |  | 2011-11-08 | 3 | 4.2 | 1.5 | 2 | 0 |  |  | 2.5 | 3 | 0.83 | Thanksgiving | 2011-11-24
| Work Days Total | 9 |  |  |  |  | 2011-11-09 | 4 | 3.5 | 1.5 | 0 | 0 |  |  | 2.5 | 4 | 0.63 | Thanks2 | 2011-11-25
| Dev Days Total | 9 |  |  |  |  | 2011-11-10 | 5 | 2.8 | 0.5 | 0 | 1 |  |  | 3.5 | 5 | 0.7 | Winter Holiday | 2011-12-26
| # of Task Work Days | 6.3 |  |  |  |  | 2011-11-14 | 6 | 2.1 | -2.5 | 0 | 3 |  |  | 6.5 | 6 | 1.08 | Winter2 | 2011-12-17
| m - Ideal Task Days Left | -0.7 |  |  |  |  | 2011-11-15 | 7 | 1.4 | -7 | 4.5 | 0 |  |  | 11 | 7 | 1.57 | New Year | 2011-12-30
| b - Ideal Task Days Left | 6.3 |  |  |  |  | 2011-11-16 | 8 | 0.7 | -8 | 0 | 1 |  |  | 12 | 8 | 1.5 | New Year2 | 2012-01-02
| m - Dev Days Used | 1 |  |  |  |  | 2011-11-17 | 9 | 0 | -11 | 2 | 1 |  |  | 15 | 9 | 1.67
| b - Dev Days Used | 0 |  |  |  |  | 2011-11-18 | 10 | -0.7 | -12 | 1 | 0 |  |  | 16 | 10 | 1.6
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status
3 |  |  |  | #N/A | #N/A | #N/A
7 |  |  |  | #N/A | #N/A | #N/A
8 |  |  |  | #N/A | #N/A | #N/A
5 |  |  |  | #N/A | #N/A | #N/A
1 |  |  |  | #N/A | #N/A | #N/A
13 |  |  |  | #N/A | #N/A | #N/A
9 |  |  |  | #N/A | #N/A | #N/A
12 |  |  |  | #N/A | #N/A | #N/A
6 |  |  |  | #N/A | #N/A | #N/A
10 |  |  |  | #N/A | #N/A | #N/A
11 |  |  |  | #N/A | #N/A | #N/A
2 |  |  |  | #N/A | #N/A | #N/A
14 |  |  |  | #N/A | #N/A | #N/A
15 |  |  |  | #N/A | #N/A | #N/A
4 |  |  |  | #N/A | #N/A | #N/A
16 |  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
| Testing, create svn tag, build release | 4
| Total Tasks Assigned | 4
| Available Time - Assigned time | 2.3
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),W2:W94)
Note on A14: Add the task ID's below

## Dec 2
| Testing and Documentation | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days John | Completed Task Days Sue | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2011-11-19 | [5 empty] | 0 | 5.6 | 4 |  |  |  |  | 0 | 0 |  | Independence | 2011-07-04 | 2026-07-29
| End Date | 2011-12-02 |  |  |  |  | 2011-11-19 | 1 | 4.9 | 4 | 0 | 0 |  |  | 0 | 1 | 0 | Labour Day | 2011-09-05
| # of Developers | 1 |  |  |  |  | 2011-11-21 | 2 | 4.2 | 3.5 | 0 | 0.5 |  |  | 0.5 | 2 | 0.25 | Veteran's Day | 2011-11-11
| Efficiency Factor | 0.7 |  |  |  |  | 2011-11-22 | 3 | 3.5 | 1.5 | 2 | 0 |  |  | 2.5 | 3 | 0.83 | Thanksgiving | 2011-11-24
| Work Days Total | 8 |  |  |  |  | 2011-11-23 | 4 | 2.8 | 1.5 | 0 | 0 |  |  | 2.5 | 4 | 0.63 | Thanks2 | 2011-11-25
| Dev Days Total | 8 |  |  |  |  | 2011-11-28 | 5 | 2.1 | 0.5 | 0 | 1 |  |  | 3.5 | 5 | 0.7 | Winter Holiday | 2011-12-26
| # of Task Work Days | 5.6 |  |  |  |  | 2011-11-29 | 6 | 1.4 | -2.5 | 0 | 3 |  |  | 6.5 | 6 | 1.08 | Winter2 | 2011-12-17
| m - Ideal Task Days Left | -0.7 |  |  |  |  | 2011-11-30 | 7 | 0.7 | -7 | 4.5 | 0 |  |  | 11 | 7 | 1.57 | New Year | 2011-12-30
| b - Ideal Task Days Left | 5.6 |  |  |  |  | 2011-12-01 | 8 | 0 | -8 | 0 | 1 |  |  | 12 | 8 | 1.5 | New Year2 | 2012-01-02
| m - Dev Days Used | 1 |  |  |  |  | 2011-12-02 | 9 | -0.7 | -11 | 2 | 1 |  |  | 15 | 9 | 1.67
| b - Dev Days Used | 0 |  |  |  |  | 2011-12-05 | 10 | -1.4 | -12 | 1 | 0 |  |  | 16 | 10 | 1.6
[7 empty] | 2011-12-06 | 11 | -2.1 | -14 | 0 | 2 |  |  | 18 | 11 | 1.64
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status
3 |  |  |  | #N/A | #N/A | #N/A
7 |  |  |  | #N/A | #N/A | #N/A
8 |  |  |  | #N/A | #N/A | #N/A
5 |  |  |  | #N/A | #N/A | #N/A
1 |  |  |  | #N/A | #N/A | #N/A
13 |  |  |  | #N/A | #N/A | #N/A
9 |  |  |  | #N/A | #N/A | #N/A
12 |  |  |  | #N/A | #N/A | #N/A
6 |  |  |  | #N/A | #N/A | #N/A
10 |  |  |  | #N/A | #N/A | #N/A
11 |  |  |  | #N/A | #N/A | #N/A
2 |  |  |  | #N/A | #N/A | #N/A
14 |  |  |  | #N/A | #N/A | #N/A
15 |  |  |  | #N/A | #N/A | #N/A
4 |  |  |  | #N/A | #N/A | #N/A
16 |  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
| Testing, create svn tag, build release | 4
| Total Tasks Assigned | 4
| Available Time - Assigned time | 1.6
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),W2:W94)
Note on A14: Add the task ID's below

## Dec 16
| Testing and Documentation | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days John | Completed Task Days Sue | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2011-12-03 | [5 empty] | 0 | 7 | 4 |  |  |  |  | 0 | 0 |  | Independence | 2011-07-04 | 2026-07-29
| End Date | 2011-12-16 |  |  |  |  | 2011-12-03 | 1 | 6.3 | 4 | 0 | 0 |  |  | 0 | 1 | 0 | Labour Day | 2011-09-05
| # of Developers | 1 |  |  |  |  | 2011-12-05 | 2 | 5.6 | 3.5 | 0 | 0.5 |  |  | 0.5 | 2 | 0.25 | Veteran's Day | 2011-11-11
| Efficiency Factor | 0.7 |  |  |  |  | 2011-12-06 | 3 | 4.9 | 1.5 | 2 | 0 |  |  | 2.5 | 3 | 0.83 | Thanksgiving | 2011-11-24
| Work Days Total | 10 |  |  |  |  | 2011-12-07 | 4 | 4.2 | 1.5 | 0 | 0 |  |  | 2.5 | 4 | 0.63 | Thanks2 | 2011-11-25
| Dev Days Total | 10 |  |  |  |  | 2011-12-08 | 5 | 3.5 | 0.5 | 0 | 1 |  |  | 3.5 | 5 | 0.7 | Winter Holiday | 2011-12-26
| # of Task Work Days | 7 |  |  |  |  | 2011-12-09 | 6 | 2.8 | -2.5 | 0 | 3 |  |  | 6.5 | 6 | 1.08 | Winter2 | 2011-12-17
| m - Ideal Task Days Left | -0.7 |  |  |  |  | 2011-12-12 | 7 | 2.1 | -7 | 4.5 | 0 |  |  | 11 | 7 | 1.57 | New Year | 2011-12-30
| b - Ideal Task Days Left | 7 |  |  |  |  | 2011-12-13 | 8 | 1.4 | -8 | 0 | 1 |  |  | 12 | 8 | 1.5 | New Year2 | 2012-01-02
| m - Dev Days Used | 1 |  |  |  |  | 2011-12-14 | 9 | 0.7 | -11 | 2 | 1 |  |  | 15 | 9 | 1.67
| b - Dev Days Used | 0 |  |  |  |  | 2011-12-15 | 10 | 0 | -12 | 1 | 0 |  |  | 16 | 10 | 1.6
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status
3 |  |  |  | #N/A | #N/A | #N/A
7 |  |  |  | #N/A | #N/A | #N/A
8 |  |  |  | #N/A | #N/A | #N/A
5 |  |  |  | #N/A | #N/A | #N/A
1 |  |  |  | #N/A | #N/A | #N/A
13 |  |  |  | #N/A | #N/A | #N/A
9 |  |  |  | #N/A | #N/A | #N/A
12 |  |  |  | #N/A | #N/A | #N/A
6 |  |  |  | #N/A | #N/A | #N/A
10 |  |  |  | #N/A | #N/A | #N/A
11 |  |  |  | #N/A | #N/A | #N/A
2 |  |  |  | #N/A | #N/A | #N/A
14 |  |  |  | #N/A | #N/A | #N/A
15 |  |  |  | #N/A | #N/A | #N/A
4 |  |  |  | #N/A | #N/A | #N/A
16 |  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
| Testing, create svn tag, build release | 4
| Total Tasks Assigned | 4
| Available Time - Assigned time | 3
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),W2:W94)
Note on A14: Add the task ID's below

## Dec 30
| Testing and Documentation | [5 empty] | Work Date | Work Days | Ideal Tasks Remaining | Actual Tasks Remaining | Completed Task Days John | Completed Task Days Sue | Completed Task Days Developer 3 | Completed Task Days Developer 4 | Total Tasks Completed | Man days used | Calculated Efficiency Factor | Holidays |  | Today Is
| Start Date | 2011-12-17 | [5 empty] | 0 | 5.6 | 4 |  |  |  |  | 0 | 0 |  | Independence | 2011-07-04 | 2026-07-29
| End Date | 2011-12-30 |  |  |  |  | 2011-12-17 | 1 | 4.9 | 4 | 0 | 0 |  |  | 0 | 1 | 0 | Labour Day | 2011-09-05
| # of Developers | 1 |  |  |  |  | 2011-12-19 | 2 | 4.2 | 3.5 | 0 | 0.5 |  |  | 0.5 | 2 | 0.25 | Veteran's Day | 2011-11-11
| Efficiency Factor | 0.7 |  |  |  |  | 2011-12-20 | 3 | 3.5 | 1.5 | 2 | 0 |  |  | 2.5 | 3 | 0.83 | Thanksgiving | 2011-11-24
| Work Days Total | 8 |  |  |  |  | 2011-12-21 | 4 | 2.8 | 1.5 | 0 | 0 |  |  | 2.5 | 4 | 0.63 | Thanks2 | 2011-11-25
| Dev Days Total | 8 |  |  |  |  | 2011-12-22 | 5 | 2.1 | 0.5 | 0 | 1 |  |  | 3.5 | 5 | 0.7 | Winter Holiday | 2011-12-26
| # of Task Work Days | 5.6 |  |  |  |  | 2011-12-23 | 6 | 1.4 | -2.5 | 0 | 3 |  |  | 6.5 | 6 | 1.08 | Winter2 | 2011-12-17
| m - Ideal Task Days Left | -0.7 |  |  |  |  | 2011-12-27 | 7 | 0.7 | -7 | 4.5 | 0 |  |  | 11 | 7 | 1.57 | New Year | 2011-12-30
| b - Ideal Task Days Left | 5.6 |  |  |  |  | 2011-12-28 | 8 | 0 | -8 | 0 | 1 |  |  | 12 | 8 | 1.5 | New Year2 | 2012-01-02
| m - Dev Days Used | 1 |  |  |  |  | 2011-12-29 | 9 | -0.7 | -11 | 2 | 1 |  |  | 15 | 9 | 1.67
| b - Dev Days Used | 0 |  |  |  |  | 2012-01-03 | 10 | -1.4 | -12 | 1 | 0 |  |  | 16 | 10 | 1.6
Task Id | Title | Estimate | Status | Get Estimate | Get Title | Get Status
3 |  |  |  | #N/A | #N/A | #N/A
7 |  |  |  | #N/A | #N/A | #N/A
8 |  |  |  | #N/A | #N/A | #N/A
5 |  |  |  | #N/A | #N/A | #N/A
1 |  |  |  | #N/A | #N/A | #N/A
13 |  |  |  | #N/A | #N/A | #N/A
9 |  |  |  | #N/A | #N/A | #N/A
12 |  |  |  | #N/A | #N/A | #N/A
6 |  |  |  | #N/A | #N/A | #N/A
10 |  |  |  | #N/A | #N/A | #N/A
11 |  |  |  | #N/A | #N/A | #N/A
2 |  |  |  | #N/A | #N/A | #N/A
14 |  |  |  | #N/A | #N/A | #N/A
15 |  |  |  | #N/A | #N/A | #N/A
4 |  |  |  | #N/A | #N/A | #N/A
16 |  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
|  |  |  | #N/A | #N/A | #N/A
| Testing, create svn tag, build release | 4
| Total Tasks Assigned | 4
| Available Time - Assigned time | 1.6
Formulas:
Work Date = WORKDAY(C2,([Work Days]-1),W2:W94)
Note on A14: Add the task ID's below

## Instructions
instructions:
http://joel.inpointform.net/software-development/burn-down-charts-tutorial-simple-agile-project-tracking/