## License
This Product Backlog and Release Plan document by John Pruitt is licensed under a Creative Commons Attribution-ShareAlike 3.0 Unported License.

## Product Backlog
Id | Feature | Business Value/Justification | Priority | Story Points | Release # | Sprint # | Done?
20 | The tool should create an initial diagram from a model. | By creating an initial version of a diagram, users won't have to start from scratch saving time. | 1 | 5 | 2 | 7 | No
21 | The tool should save diagrams to a JavaScript file. | Diagrams should be persistant, and users shouldn't have to write files by hand. | 1 | 2 | 2 | 7 | No
24 | The GUI should have a toolbar and menubar allowing the user to open models, create, open, save, and close diagrams. | This is an expected/standard feature in GUIs. | 1 | 3 | 2 | 7 | No
27 | The GUI should allow the user to Pan and Zoom within a diagram. | Diagrams can get big, and users need to be able to move around within them. | 1 | 5 | 2 | 7 | No
22 | Users should be able to move/rearrange Tables and ForeignKeys in a diagram. | Users need to be able to layout diagrams according to what makes sense to them. | 2 | 3 | 2 | 8 | No
25 | Users should be able to resize Tables in a diagram. | The tool should do its best, but users should be able to adjust per their judgement. | 2 | 2 | 2 | 8 | No
23 | Users should be able to add/remove elements (Tables ForeignKeys) from a diagram. | You don't always want to show everything in a single diagram. | 3 | 5 | 2 | 8 | No
26 | Schemas should be optionally displayed in diagrams. | Showing schemas can help explain a model. | 3 | 2 | 2 | 8 | No
29 | Add graphical elements to display datatype, nullability, foreign key types, etc. | Expected in database diagrams, these details expose the model. | 4 | 5 | 2 | 8 | No
28 | A separate "Model Explorer" window should allow users to see the details of all elements in a model using a tree view and grid. | Details are important and cannot always be displayed in a graphical diagram. A supplement is necessary. | 4 | 5 | 2 | 9 | No
13 | Diagrams should be able to be saved to an image format or possibly a PDF for distribution. | Many people who don't need to create models may need to view a diagram of the model. They shouldn't have to have the tool installed. | 4 | 5 | 2 | 9 | No
6 | The tool should be able compare a model against an existing database schema to show the differences. | When a model and a database get out of sync, you need an automated way to check for deltas. To slow and error-prone to be done manually. | 5 | 8 | 2 | 9 | No
17 | Refactor the core library. Separate Fluent API from data structures. Comment and unit test code. | All other features will build upon these core classes. They need to be cleanly designed and implemented. | 5 | 5 | 2 | 10 | No
14 | The tool should be able to export a diagram with model and data dictionary information to a static, readonly webpage format that can be hosted on a website. You should be able to view the diagram in a browser and explore the model details. | Many people who don't need to create models may need to view a diagram of the model. They shouldn't have to have the tool installed. | 6 | 34 | 2 | 10 | No
3 | A DA needs to be able to create a naming standard, which defines the format used for the names of schema objects and defines standard abbreviations for words. This should be reusable; multiple models should be able to use the same naming standard. | Most companies have naming standards to which database models must comply. It would be beneficial to manage this standard with the same tool in which models are defined. | x | x | x |  | No
9 | The naming standard should be stored in a human-readable/writable text format.tools. | Text is the most efficient editing medium and can be easily managed with regular version control | x | x | x |  | No
4 | The tool should be able to check the names in the model against the naming standards and report any deviations. | Manually checking each element of a model against standards is inefficient and error-prone. An automated check is highly beneficial. | x | x | x |  | No
1 | A data architect (DA) needs to define tables, columns, and constraints in a model. | This is the core of what is needed in a database model. | x | 5 | 1 | 1 | Yes
15 | The tool should be released under an open-source license and hosted on a major site like BitBucket, or Google Code. | Using an open-source license and a well-know hosting site will increase the visibility/usefulness of the project. I don't have the facilities to host the project myself anyway. | x | 1 | 1 | 1 | Yes
7 | The model should be stored in a human-readable/writable text format. | Text is the most efficient editing medium and can be easily managed with regular version control tools. | x | 2 | 1 | 2 | Yes
16 | The tool should provide a REPL for manipulating/querying the model interactively | Interactive, programmatic access will allow programmers to do certain tasks very efficiently that would otherwise be quite manual | x | 3 | 1 | 2 | Yes
10 | There should be an API for querying and perhaps manipulating model objects so that programmers can extend the tool, perform one-off tasks with scripting languages, and/or build code generation tools. | This is the value+ feature of the product. Allowing scripting access to a model provides a way to perform all sorts of productive activities. | x | 3 | 1 | 2 | Yes
2 | A DA needs to create a data dictionary for a model containing metadata: descriptions of tables, columns, etc. | The data dictionary provides documentation of the model. It explains what the structures mean in business terms. An essential feature. | x | 1 | 1 | 3 | Yes
8 | The data dictionary should be stored in a human-readable/writable text format. | Text is the most efficient editing medium and can be easily managed with regular version control tools. | x | 0 | 1 | 3 | Yes
5 | The tool should automatically generate DDL for a particular platform based on the model. | Writing DDL by hand is slow and error-prone. It is also not portable between different db platforms. The tool should do this. | x | 3 | 1 | 5 | Yes
18 | Prepare and deliver Release #1 | Required for class. | x | 2 | 1 | 5 | Yes
19 | A DA needs to be able to view diagrams of a model in a GUI. | A picture is worth a thousand words. | x | 5 | 2 | 6 | Yes
12 | Diagram definitions should be stored in a human-readable text format. | So that changes can be managed with regular version control tools. | x | 5 | 2 | 6 | Yes
29 |  |  |  | 119

## Release Plan
Release |  | Sprint | Theme | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Done | Story Pts. | Est. Hrs. | Act. Hrs.
Core library and Model Creation/Manipulation | Release 1 | Sprint 1 | Project Setup + Core Library | 2011-01-09 | 2011-01-10 | 2011-01-11 | 2011-01-12 | 2011-01-13 | 2011-01-14 | 2011-01-15 | Y | 6 | 9.5 | 13.25
|  | Sprint 2 | Model API | 2011-01-16 | 2011-01-17 | 2011-01-18 | 2011-01-19 | 2011-01-20 | 2011-01-21 | 2011-01-22 | Y | 8 | 10 | 7.5
|  | Sprint 3 | Refactoring + DDL Generation | 2011-01-23 | 2011-01-24 | 2011-01-25 | 2011-01-26 | 2011-01-27 | 2011-01-28 | 2011-01-29 | N | 7 | 11.25 | 5.25
|  | Sprint 4 | Refactoring | 2011-01-30 | 2011-01-31 | 2011-02-01 | 2011-02-02 | 2011-02-03 | 2011-02-04 | 2011-02-05 | N | 4 | 5.25 | 5.5
|  | Sprint 5 | DDL Generation | 2011-02-06 | 2011-02-07 | 2011-02-08 | 2011-02-09 | 2011-02-10 | 2011-02-11 | 2011-02-12 | Y | 5 | 6.5 | 5.25
Diagramming | Release 2 | Sprint 6 | Cmd Line Options + Diagram Viewing | 2011-02-13 | 2011-02-14 | 2011-02-15 | 2011-02-16 | 2011-02-17 | 2011-02-18 | 2011-02-19 | Y | 15 | 13 | 9.75
|  |  |  | 2011-02-20 | 2011-02-21 | 2011-02-22 | 2011-02-23 | 2011-02-24 | 2011-02-25 | 2011-02-26
|  | Sprint 7 | Diagram Creation & Storage + GUI Niceties | 2011-02-27 | 2011-02-28 | 2011-03-01 | 2011-03-02 | 2011-03-03 | 2011-03-04 | 2011-03-05 |  | 15
|  |  |  | 2011-03-06 | 2011-03-07 | 2011-03-08 | 2011-03-09 | 2011-03-10 | 2011-03-11 | 2011-03-12
|  | Sprint 8 | Diagram Editing | 2011-03-13 | 2011-03-14 | 2011-03-15 | 2011-03-16 | 2011-03-17 | 2011-03-18 | 2011-03-19 |  | 17
|  |  |  | 2011-03-20 | 2011-03-21 | 2011-03-22 | 2011-03-23 | 2011-03-24 | 2011-03-25 | 2011-03-26
|  | Sprint 9 | Diagram Export + Model Explorer + Database Compare | 2011-03-27 | 2011-03-28 | 2011-03-29 | 2011-03-30 | 2011-03-31 | 2011-04-01 | 2011-04-02 |  | 18
|  |  |  | 2011-04-03 | 2011-04-04 | 2011-04-05 | 2011-04-06 | 2011-04-07 | 2011-04-08 | 2011-04-09
|  | Sprint 10 | ? | 2011-04-10 | 2011-04-11 | 2011-04-12 | 2011-04-13 | 2011-04-14 | 2011-04-15 | 2011-04-16 |  | 39
|  |  |  | 2011-04-17 | 2011-04-18 | 2011-04-19 | 2011-04-20 | 2011-04-21 | 2011-04-22 | 2011-04-23
Formulas:
Sun = [Sun, row above]+7
Mon = [Mon, row above]+7
Tues = [Tues, row above]+7
Wed = [Wed, row above]+7
Thurs = [Thurs, row above]+7
Fri = [Fri, row above]+7
Sat = [Sat, row above]+7

## Data
Sprint | Date | Ideal | Est. Hours Done | Est. Hours Left | Act. Hrs Worked | Cumulative Act. Hrs Worked
1 | 2011-01-08 | 9.5 | 0 | 9.5 | 0 | 0
1 | 2011-01-09 | 8.1429 | 0.5 | 9 | 1 | 1
1 | 2011-01-10 | 6.7857 | 2 | 7 | 1.75 | 2.75
1 | 2011-01-11 | 5.4286 | 1 | 6 | 2 | 4.75
1 | 2011-01-12 | 4.0714 | 0 | 6 | 0 | 4.75
1 | 2011-01-13 | 2.7143 | 0 | 6 | 0.5 | 5.25
1 | 2011-01-14 | 1.3571 | 0 | 6 | 2 | 7.25
1 | 2011-01-15 | 0 | 6 | 0 | 6 | 13.25
2 | 2011-01-15 | 10 | 0 | 10 | 0 | 0
2 | 2011-01-16 | 8.5714 | 0 | 10 | 1 | 1
2 | 2011-01-17 | 7.1429 | 0 | 10 | 2.25 | 3.25
2 | 2011-01-18 | 5.7143 | 9 | 1 | 2.5 | 5.75
2 | 2011-01-19 | 4.2857 | 0 | 1 | 0 | 5.75
2 | 2011-01-20 | 2.8571 | 0 | 1 | 0 | 5.75
2 | 2011-01-21 | 1.4286 | 0 | 1 | 0 | 5.75
2 | 2011-01-22 | 0 | 1 | 0 | 1 | 6.75
3 | 2011-01-22 | 11.25 | 0 | 11.25 | 0 | 0
3 | 2011-01-23 | 9.6429 | 0 | 11.25 | 0 | 0
3 | 2011-01-24 | 8.0357 | 0 | 11.25 | 2 | 2
3 | 2011-01-25 | 6.4286 | 0 | 11.25 | 0 | 2
3 | 2011-01-26 | 4.8214 | 3.75 | 7.5 | 1.75 | 3.75
3 | 2011-01-27 | 3.2143 | 0 | 7.5 | 1.5 | 5.25
3 | 2011-01-28 | 1.6071 | 0 | 7.5 | 0 | 5.25
3 | 2011-01-29 | 0 | 0 | 7.5 | 0 | 5.25
4 | 2011-01-29 | 5.25 | 0 | 5.25 | 0 | 0
4 | 2011-01-30 | 4.5 | 1.25 | 4 | 1.5 | 1.5
4 | 2011-01-31 | 3.75 | 0 | 4 | 1.5 | 3
4 | 2011-02-01 | 3 | 0 | 4 | 0 | 3
4 | 2011-02-02 | 2.25 | 0 | 4 | 0.25 | 3.25
4 | 2011-02-03 | 1.5 | 0 | 4 | 0.5 | 3.75
4 | 2011-02-04 | 0.75 | 0 | 4 | 0.25 | 4
4 | 2011-02-05 | 0 | 1.5 | 2.5 | 1.5 | 5.5
5 | 2011-02-05 | 6.5 | 0 | 6.5 | 0 | 0
5 | 2011-02-06 | 5.5714 | 0 | 6.5 | 0 | 0
5 | 2011-02-07 | 4.6429 | 0 | 6.5 | 0 | 0
5 | 2011-02-08 | 3.7143 | 0 | 6.5 | 0 | 0
5 | 2011-02-09 | 2.7857 | 3.17 | 3.33 | 2.5 | 2.5
5 | 2011-02-10 | 1.8571 | 3.33 | 0 | 2.75 | 5.25
5 | 2011-02-11 | 0.92857 | 0 | 0 | 0 | 5.25
5 | 2011-02-12 | 0 | 0 | 0 | 0 | 5.25
6 | 2011-02-12 | 13 | 0 | 13 | 0 | 0
6 | 2011-02-13 | 12.0714 | 0 | 13 | 0 | 0
6 | 2011-02-14 | 11.1429 | 0 | 13 | 0 | 0
6 | 2011-02-15 | 10.2143 | 0 | 13 | 0 | 0
6 | 2011-02-16 | 9.2857 | 4 | 9 | 3 | 3
6 | 2011-02-17 | 8.3571 | 0 | 9 | 0 | 3
6 | 2011-02-18 | 7.4286 | 0 | 9 | 0 | 3
6 | 2011-02-19 | 6.5 | 0 | 9 | 0 | 3
6 | 2011-02-20 | 5.5714 | 0 | 9 | 0 | 3
6 | 2011-02-21 | 4.6429 | 3.5 | 5.5 | 2.5 | 5.5
6 | 2011-02-22 | 3.7143 | 0 | 5.5 | 2 | 7.5
6 | 2011-02-23 | 2.7857 | 0 | 5.5 | 0 | 7.5
6 | 2011-02-24 | 1.8571 | 0 | 5.5 | 0 | 7.5
6 | 2011-02-25 | 0.92857 | 0 | 5.5 | 0 | 7.5
6 | 2011-02-26 | -1.5543e-15 | 5.5 | 0 | 2.25 | 9.75