## Product Backlog
Id | Feature | Business Value | Priority | Story Points | Release # | Sprint #
1 | A data architect (DA) needs to define tables, columns, and constraints in a model. | This is the core of what is needed in a database model. | 1 | 5 | 1 | 1
15 | The tool should be released under an open-source license and hosted on a major site like BitBucket, or Google Code. | Using an open-source license and a well-know hosting site will increase the visibility/usefulness of the project. I don't have the facilities to host the project myself anyway. | 1 | 1 | 1 | 1
7 | The model should be stored in a human-readable/writable text format. | Text is the most efficient editing medium and can be easily managed with regular version control tools. | 2 | 2 | 1 | 2
16 | The tool should provide a REPL for manipulating/querying the model interactively | Interactive, programmatic access will allow programmers to do certain tasks very efficiently that would otherwise be quite manual | 2 | 3 | 1 | 2
10 | There should be an API for querying and perhaps manipulating model objects so that programmers can extend the tool, perform one-off tasks with scripting languages, and/or build code generation tools. | This is the value+ feature of the product. Allowing scripting access to a model provides a way to perform all sorts of productive activities. | 2 | 3 | 1 | 2
5 | The tool should automatically generate DDL for a particular platform based on the model. | Writing DDL by hand is slow and error-prone. It is also not portable between different db platforms. The tool should do this. | 3 | 3 | 1 | 3
2 | A DA needs to create a data dictionary for a model containing metadata: descriptions of tables, columns, etc. | The data dictionary provides documentation of the model. It explains what the structures mean in business terms. An essential feature. | 5 | 2 | 1 | 4
8 | The data dictionary should be stored in a human-readable/writable text format. | Text is the most efficient editing medium and can be easily managed with regular version control tools. | 5 | 2 | 1 | 4
11 | A DA needs to create diagrams depicting the model graphically. Ideally, a GUI would be used to create diagrams. | A picture is worth a thousand words. | 4 | 21 | 1
12 | Diagram definitions should be stored in a human-readable text format. | So that changes can be managed with regular version control tools. | 4 | 13 | 1
6 | The tool should be able compare a model against an existing database schema to show the differences. | When a model and a database get out of sync, you need an automated way to check for deltas. To slow and error-prone to be done manually. | 6 | 8 | 1
3 | A DA needs to be able to create a naming standard, which defines the format used for the names of schema objects and defines standard abbreviations for words. This should be reusable; multiple models should be able to use the same naming standard. | Most companies have naming standards to which database models must comply. It would be beneficial to manage this standard with the same tool in which models are defined. | 6 | 3 | 1
9 | The naming standard should be stored in a human-readable/writable text format.tools. | Text is the most efficient editing medium and can be easily managed with regular version control | 6 | 2 | 1
4 | The tool should be able to check the names in the model against the naming standards and report any deviations. | Manually checking each element of a model against standards is inefficient and error-prone. An automated check is highly beneficial. | 6 | 1 | 1
13 | Diagrams should be able to be saved to an image format or possibly a PDF for distribution. | Many people who don't need to create models may need to view a diagram of the model. They shouldn't have to have the tool installed. | 6 | 13 | 1
14 | The tool should be able to export a diagram with model and data dictionary information to a static, readonly webpage format that can be hosted on a website. You should be able to view the diagram in a browser and explore the model details. | Many people who don't need to create models may need to view a diagram of the model. They shouldn't have to have the tool installed. | 6 | 34 | 1
17 | Create a junit test suite for the core library |  | 6 | 5
18 | Comment the core library and produce javadocs |  | 6 | 5

## Sprint 1 Tasks
Task Id | User Story Id | Task Description | Estimate | Actual | Date Done | Note
1 | 15 | Research and choose an open-source license to use. | 0.5 | 1 | 2011-01-09 | Use the MIT license
2 | 15 | Research and choose a site to host the project. BitBucket or Google Code. Must have good support for Mercurial. | 0.5 | 0.5 | 2011-01-10 | BitBucket
3 | 15 | Choose a name for the project. Create an account and initial project on hosting site. | 1 | 0.25 | 2011-01-10 | "com.jgpruitt.datamodeler"
4 | 1 | Research and choose a Java IDE. Netbeans, Eclipse, or IntelliJ CE. | 0.5 | 1 | 2011-01-10 | IntelliJ CE
5 | 1 | Project setup: Create project structure. Create project in IDE. Import into Mercurial. | 1 | 2 | 2011-01-11
6 | 1 | Code to represent a "DataType" | 0.5 | 0.5 | 2011-01-15
7 | 1 | Code to represent a "Column" | 0.5 | 1.5 | 2011-01-15
8 | 1 | Code to represent a "Table" | 1 | 1.5 | 2011-01-15
9 | 1 | Code to represent an "Index" | 1 | 1 | 2011-01-15
10 | 1 | Code to represent a "Primary Key Constraint" | 0.5 | 1 | 2011-01-15
11 | 1 | Code to represent a "Unique Constraint" | 0.5 | 1 | 2011-01-15
12 | 1 | Code to represent a "Foreign Key Constraint" | 1 | 1 | 2011-01-15
13 | 1 | Code to represent a "Schema" | 0.5 | 0.5 | 2011-01-15
14 | 1 | Code to represent a "Model" | 0.5 | 0.5 | 2011-01-15

## Sprint 1 Burndown
Date | Ideal | Est. Hours Done | Est. Hours Left | Act. Hrs Worked | Cumulative Act. Hrs Worked
2011-01-08 | 9.5 | 0 | 9.5 | 0 | 0
2011-01-09 | 8.1429 | 0.5 | 9 | 1 | 1
2011-01-10 | 6.7857 | 2 | 7 | 1.75 | 2.75
2011-01-11 | 5.4286 | 1 | 6 | 2 | 4.75
2011-01-12 | 4.0714 | 0 | 6 | 0 | 4.75
2011-01-13 | 2.7143 | 0 | 6 | 0.5 | 5.25
2011-01-14 | 1.3571 | 0 | 6 | 2 | 7.25
2011-01-15 | 0 | 6 | 0 | 6 | 13.25