## Product Backlog
Id | Feature | Business Value | Priority | Story Points | Release # | Sprint # | Done?
5 | The tool should automatically generate DDL for a particular platform based on the model. | Writing DDL by hand is slow and error-prone. It is also not portable between different db platforms. The tool should do this. | 1 | 3 | 1 | 5 | No
18 | Prepare and deliver Release #1 | Required for class. | 1 | 2 | 1 | 5 | No
11 | A DA needs to create diagrams depicting the model graphically. Ideally, a GUI would be used to create diagrams. | A picture is worth a thousand words. | 2 | 21 | 2 |  | No
12 | Diagram definitions should be stored in a human-readable text format. | So that changes can be managed with regular version control tools. | 3 | 13 | 2 |  | No
13 | Diagrams should be able to be saved to an image format or possibly a PDF for distribution. | Many people who don't need to create models may need to view a diagram of the model. They shouldn't have to have the tool installed. | 4 | 13 | 2 |  | No
17 | Refactor the core library. Separate Fluent API from data structures. Comment and unit test code. | All other features will build upon these core classes. They need to be cleanly designed and implemented. | 6 | 4 | 1 | 4 | No
6 | The tool should be able compare a model against an existing database schema to show the differences. | When a model and a database get out of sync, you need an automated way to check for deltas. To slow and error-prone to be done manually. | 6 | 8 | 2 |  | No
3 | A DA needs to be able to create a naming standard, which defines the format used for the names of schema objects and defines standard abbreviations for words. This should be reusable; multiple models should be able to use the same naming standard. | Most companies have naming standards to which database models must comply. It would be beneficial to manage this standard with the same tool in which models are defined. | 6 | 3 | 2 |  | No
9 | The naming standard should be stored in a human-readable/writable text format.tools. | Text is the most efficient editing medium and can be easily managed with regular version control | 6 | 2 | 2 |  | No
4 | The tool should be able to check the names in the model against the naming standards and report any deviations. | Manually checking each element of a model against standards is inefficient and error-prone. An automated check is highly beneficial. | 6 | 1 | 2 |  | No
14 | The tool should be able to export a diagram with model and data dictionary information to a static, readonly webpage format that can be hosted on a website. You should be able to view the diagram in a browser and explore the model details. | Many people who don't need to create models may need to view a diagram of the model. They shouldn't have to have the tool installed. | 6 | 34 | 2 |  | No
1 | A data architect (DA) needs to define tables, columns, and constraints in a model. | This is the core of what is needed in a database model. | x | 5 | 1 | 1 | Yes
15 | The tool should be released under an open-source license and hosted on a major site like BitBucket, or Google Code. | Using an open-source license and a well-know hosting site will increase the visibility/usefulness of the project. I don't have the facilities to host the project myself anyway. | x | 1 | 1 | 1 | Yes
7 | The model should be stored in a human-readable/writable text format. | Text is the most efficient editing medium and can be easily managed with regular version control tools. | x | 2 | 1 | 2 | Yes
16 | The tool should provide a REPL for manipulating/querying the model interactively | Interactive, programmatic access will allow programmers to do certain tasks very efficiently that would otherwise be quite manual | x | 3 | 1 | 2 | Yes
10 | There should be an API for querying and perhaps manipulating model objects so that programmers can extend the tool, perform one-off tasks with scripting languages, and/or build code generation tools. | This is the value+ feature of the product. Allowing scripting access to a model provides a way to perform all sorts of productive activities. | x | 3 | 1 | 2 | Yes
2 | A DA needs to create a data dictionary for a model containing metadata: descriptions of tables, columns, etc. | The data dictionary provides documentation of the model. It explains what the structures mean in business terms. An essential feature. | x | 1 | 1 | 3 | Yes
8 | The data dictionary should be stored in a human-readable/writable text format. | Text is the most efficient editing medium and can be easily managed with regular version control tools. | x | 0 | 1 | 3 | Yes

## Sprint 5 Tasks
Task Id | User Story Id | Task Description | Optimistic | Most Likely | Pessimistic | Estimate | Actual | Date Done | Note
1 | 5 | Create code to generate DDL for a SQLite database | 2 | 3 | 5 | 3.1667 | 2.25 | 2011-02-09
2 | 5 | Create tests scripts to test DDL generation | 0.5 | 1 | 2 | 1.0833 | 1 | 2011-02-10
3 | 18 | Create a demo video | 0.5 | 1 | 2 | 1.0833 | 1 | 2011-02-10
4 | 18 | Do a release review post. | 1 | 1 | 2 | 1.1667 | 1 | 2011-02-10
[6 empty] | 6.5 | 5.25

## Sprint 5 Burndown
| Date | Ideal | Est. Hours Done | Est. Hours Left | Act. Hrs Worked | Cumulative Act. Hrs Worked
Sat | 2011-02-05 | 6.5 | 0 | 6.5 | 0 | 0
Sun | 2011-02-06 | 5.5714 | 0 | 6.5 | 0 | 0
Mon | 2011-02-07 | 4.6429 | 0 | 6.5 | 0 | 0
Tues | 2011-02-08 | 3.7143 | 0 | 6.5 | 0 | 0
Wed | 2011-02-09 | 2.7857 | 3.17 | 3.33 | 2.5 | 2.5
Thurs | 2011-02-10 | 1.8571 | 3.33 | 0 | 2.75 | 5.25
Fri | 2011-02-11 | 0.92857 | 0 | 0 | 0 | 5.25
Sat | 2011-02-12 | 0 | 0 | 0 | 0 | 5.25

## Retro
Sprint | Est. Hrs. | Act. Hrs.
Sprint 1 | 9.5 | 13.25
Sprint 2 | 10 | 7.5
Sprint 3 | 11.25 | 5.25
Sprint 4 | 5.25 | 5.5
Sprint 5 | 6.5 | 5.25