## 工作表1
Risk Register
Code | Level/Score | Risk name | Description | Potential Impact | Classification | Root | Trigger | Response strategy | Risk owner | Probability | Consequence | State
R2 | 6 | Network problem | Users cannot access the system because of the fail connection to database servers | Benefit lost | Technical | Database servers cannot be accessed | Client has no database experience so he can not connect to the database | Ask project team or IT staff to help client. | Web manager | Mediem | High | Not happen
R5 | 4 | Scope definition | There are errors or omissionin scope definition | Wrong deliverables and project delays | Project Management | Team does not identify or classify tasks properly | Tasks do not improve or slightly improve project | Re-define scope and communicate with client every week. Check with Doomsayer regularly. | Doomsayer | Mediem | Mediem | Performming weekly group meeting and client meeting.
R1 | 3 | Product's data loss | Product's data disappears due to inevitable accident | The website can not show the right list | Programmer | Thousands of data in the file | Programmer's omission about the data file | Ask client to send the data file agin | Project Manager | Low | High | Not happen
R3 | 3 | Early completion of project | The project completes before the delivered date | Save cost and time | Project Management | Team members finish tasks early. | 1.Team members finish majority of tasks early. 2. The project is easier than expectation. | Encourage team members when project finishes. | Team | Low | High | Not happen
R4 | 3 | Delay of project | The project cannot complete on time | 1.Cost increases 2. Discontented clients 3. Extended develop time | Project Management | Team members cannot finish major tasks. The project is difficult than expectation. | Approximately 1/3 tasks cannot finish on time | 1.Learn from the failure 2. Explain to client why project delay 3.Negotiate main stakeholders for an extention | Team | Low | High | Not happen
R6 | 2 | Team member's resignation | Team members resign from the team | Project delays | Project Management | Uncomfortable with other team members | Team members do not engage team work actively. | Ask tutor to resovel this problem | Project Manager | Low | High | Not happen
Higher level/score means higher probability or more sever consequence or both.
| 3 | High
Probability | 2 | Medium |  | R5 | R2
| 1 | Low |  | R6 | R1,R3,R4
|  |  | Low | Medium | High
|  |  | 1 | 2 | 3
Consequence
Note on B2: Higher level/score means higher probability or more sever consequence or both. -Xing DENG